## Introduction (hidden)
IRP 24 Hazard Register
Column Headings
Column Letter
Item | A | Sequential item number for hazards in each operational phase.
Hazard Scenario What If | B | Single jeopardy statement used to identify potential problems due to failure in pre-job planning, training, procedures, or equipment failure.
Applicable | C | Choose "Y" if "Hazard Scenario What If" applies to operation and "N" if it does not.
Threats/Consequences | D | A list of the potential consequences (HSE and NPT) of the "what if" occurring.
HSE | E | The risk of a situation/event with the potential to cause harm (to people, assets, or the environment).
NPT | F | The risk of Non Productive Time (NPT), including lost time and costs, formation damage and/or any deviation from the plan.
Required HSE Critical Controls / Safeguards | G | Controls/safeguards, and detailed recommended practices for high risk HSE items and referenced to specific prescriptive IRP 24 enforced requirements.
Considerations | H | Recommendations, considerations, and informational statements on how to reduce, eliminate, or manage Medium/Low Risk HSE items and all NPT items.
Actions to be Taken / By Who and When | I | List of actions required to reduce/eliminate the potential occurrence and/or severity if the hazard cannot be eliminated entirely. Who = Party/parties responsible for each action assigned. When = Date by which the action is to be completed.
Operational Phase | J | Categorization of the hazard scenario by operational phase.
Primary Responsible Party | K | Categorization of the hazard scenario by primary responsible party.
Primary Category | L | Categorization of the hazard scenario by primary category (equipment, well program, etc.)
Risk Ranking - severity of the event (consequence multiplied by likelihood of occurrence)
1 |  | High Risk - Engineering, Procedures, and Training required to control/mitigate risk.
2 |  | Medium Risk - Procedures and Training required to control/mitigate risk. Should consider Engineering.
3 |  | Low Risk - Training required to control/mitigate risk. Should consider Engineering and Procedures.
General Notes about Register

## Subject Well Integrity
Item | Sub IRP | Category | Position | Hazard Scenario What is existing? | Applicable | Cause How can this happen? | Threats / Consequences What events/incidents can result? | HSE | NPT | Required HSE Critical Controls / Safeguards | Industry Suggested Controls and Mitigations How can this be prevented? | Actions to be taken / By Who and When | Frequency of Exposure | Probability of Loss | Consequences | Risk Ranking | Operational Phase | Primary Responsible Party | Related to Item
Example |  |  |  | Incorrect barrier envelope AMP |  | - Inadequate assessment of the condition of a barrier element - Missing a barrier element in the assessment - inadequate assessment of the condition of the well, downhole environment (such as exposure to H2S), and/or the potential forces and loading conditions - erosion, corrosion, mechanical wear - plastic formations (e.g., salt formations) - high pressure / low permeability formations | - Loss of barrier envelope integrity in the SW | 1 | 1 |  | `- Re-assess Subject Well history and how it affects the condition of barrier elements - Conduct pressure integrity tests to better assess the condition of a barrier element - Run logs to better assess the condition of a barrier element - Review the flowpath to capture all barrier elements - Review force analysis to ensure inclusion of all loading conditions such as temperature induced stresses from the fracture fluids - Review downhole environmental exposure conditions to determine appropriate reductions in barrier element integrity - Conduct a proper assessment of minimum external pressures to determine net burst pressures. - Consider hydrostatic column of treating slurry - Review the fracture stimulation program treatment rates and pressures to assure a appropriate/conservative estimate of maximum treament pressure. | [7 empty] | 24.2.2.1 Subject Well Barrier Analysis

## Interwellbore Communication (hidden)
Item | Sub IRP | Category | Position | Hazard Scenario What is existing? | Applicable | Cause How can this happen? | Threats / Consequences What events/incidents can result? | HSE | NPT | Required HSE Critical Controls / Safeguards | Industry Suggested Controls and Mitigations How can this be prevented? | Actions to be taken / By Who and When | Frequency of Exposure | Probability of Loss | Consequences | Risk Ranking | Operational Phase | Primary Responsible Party | Related to Item
1 | Other |  |  | Frac equipment refueling hose/line leaks | Y | - Hose/line failure due to fittings incorrectly installed - Hose/line not integrity tested prior to use - Fatigue failure of hose/line - Hose/line degradation due to lack of proper inspection process - Damage to fuel lines/hose from mobile equipment on wellsite | - Hose/line failure due to fittings incorrectly installed - Hose/line not integrity tested prior to use - Fatigue failure of hose/line - Hose/line degradation due to lack of proper inspection process - Damage to fuel lines/hose from mobile equipment on wellsite |  |  |  | -appropriate fire suppression on location (number of fire trucks for number of pumps)
2 | Other |  |  | Treating Line failure | Y | -Screenout, plugged line, frozen line, electronic failure, improper trip settings, relief valve failure, overpressure, washout, improper rig-in, miss-matched unions | - Fire and explosion - Harm to personnel - Lost time and cost - Damage to equipment |  |  | Pressure relief valve, | Pressure relief valve, iron mgmt and testing standards, rig-in standards (sufficient flexibility, tie-downs, flow capacity etc), flowback requirements, no personnel in high pressure zone
3 | Other |  |  | Chemical Spill | Y | -Valve failure, rupture of tote, line failure, washout, seal failure | Environmental, harm to personnel, lost time and cost |  |  | - PPE, fire suppression equipment, containment in chem vans, shower units | - Control toxicity of chemicals being used/chemical substitution, visual inspection of chem add hoses, stainless steel fittings (engineering controls), spill kits and training, order of addition for chemicals
4 | Other |  |  | Fire in chem van | Y | -release of low flash point chemical, use of alcohol to suppress freeze point, frozen chem add line, mixture of incompatible products | -Environment, harm to personnel, fire, damage to equipment |  |  | - PPE, fire suppression equipment, containment in chem vans, shower units | -Standards for chem add packages in specific environments, standards for segregation of products during transport
5 | Other |  |  | Well control failure at wellhead | Y | Wellhead component failure, treating line failure, testing equipment failure, overpressure, washout, communication with offsetting well | - Fire and explosion - Harm to personnel - Lost time and cost - Damage to equipment |  |  |  | - Remote operated wellhead valve, redundant wellhead valves, treesaver, properly configured wellhead stacks (large enough ports/connections)
6 | Other |  |  | CO2/N2 release | Y | -Suction hose failure, containment vessel failure, treating line failure | Harm to personnel, damage to equipment |  |  | Proper venting/relief valves on tanks, iron & hose testing/standards | -Standard for tank bleedoff at end of job
7 | Other |  |  | Packing failure | Y | Improper maintenance, improper packing, wrong packing material, inadequate lubrication | - Fire and explosion - Harm to personnel - Lost time and cost - Damage to equipment |  |  | Maintenance standards, training, Pump ESD's | -Head tarps, pump covers
8 | Simultaneous Operations |  |  | Concurrent operation | Y | Small leases, multiple wells per lease, efficiency |  |  |  |  | -Wellhead spacing regulations, consideration for acceptable simultaneous ops, egress plans
9 | Other |  |  | Pumping recirculated fluids | Y |  | H2S exposure, flammability, damage to equipment/treating iron, unknown contaminants (required PPE) |  |  |  | -standard for frac water, MSDS requirement, minimum sampling and testing requirements
10 | Other |  |  | Prolonged exposure to silica sand | Y | Larger fracs and multiple zones require in the multiple of 10 times the volume of sand | Exposure above the OEL to workers of Silica sand |  |  | Increased PPE respiratory protection | Exposure monitoring, and health assessment monitoring.
11 | Other |  |  | High pressure frac line failure clean side | Y | water cannon effect
12 | Other |  |  | High pressure frac line failure dirty side | Y | cannon effective containing possible corrosives or sand
13 | Other |  |  | High pressure frac union or fitting failure | Y | both clean and dirty side
14 | Other |  |  | Ice plugs or hydrates forming in frac line | Y
15 | Other |  |  | High pressure lines whipping around following a failure or separation | Y
16 | Other |  |  | Chemical or corrosive release high volume/low volume | Y
17 | Other |  |  | Vapour release high volume or low volume, high pressure and low pressure (propane frac) | Y
18 | Other |  |  | The special case of hydraulic fracture stimulating in shallow wells, particularly those at target depths less than 600 m or within 300 m of the base of groundwater protection is cause for concern and very careful evaluations are required. | Y
1 |  |  |  | FPZ is Underestimated |  | - See Appendix A of IRP 24 document - Geology - Inadequate Modeling - Fracture Treatment Larger than planned - Multiple stages pumped into one stage unintentionally (inadequate stage isolation, frac goes only into one perforated interval on a multi-perforated stage, longitudinal frac, hz pancake frac) - Fracture Treatment type change from plan - Intersection of offset hydraulically fractured wellbores - FPZ reservoir depletion | - Loss of barrier integrity in an IOW - Unintentional interwellbore communication - Fault(s) can considerably extend fracture half length, thus increasing the likelihood of interwellbore communication to wells within the FPZ and beyond the FPZ (i.e., a fault can create FPZ estimation uncertainty) '- Packer or cement failing to isolate frac into desired interval - Ball activated system failure (ball not dropped, ball fails, downhole seat fails). Wrong ball dropped on sleeve. Extra ball in system accidentally left over from another well's frac operation - Friction diversion not working for limited entry frac - Seat is worn on ball/seat job so ball does not shift sleeve - Coil fraccing downhole isolation packer/tool fails and bypasses to previously fracced stages below it | 1 | 1 |  | - If faulting is anticipated, establish IOW well control plans based on a higher likelihood of interwellbore communication - Compile area experience for more accurate FPZ determination - Consider adding a fault related safety factor to intentionally expand the FPZ - If faulting is anticipated, consider all possible SCW's as at-risk - Micro-seismic to asses frac propagation behaviour when perforating multiple intervals for a single frac stage | [8 empty] | 1
2 |  |  |  | Adjusted Maximum Pressure (AMP) Overestimation |  | - No recent pressure integrity tests conducted - Challenges with determining Adjusted Maximum Pressure on a barrier flow path based on operational history of component (how to effectively derate a component) - Casing and/or downhole equipment integrity issues due to corrosion, erosion, service, & age - Wellhead integrity problems due to corrosion, erosion, service, and age | - Loss of barrier integrity in an IOW - Inadequate allowance for response times during wellsite operations to prevent adjusted maximum pressure from being exceeded - Pressure integrity reliability of threaded components | 1 | 1 |  | - Conduct pressure integrity tests to verify Adjusted Maximum Pressure - Replace (if possible) barrier components of concern that have been integrity tested to the Adjust Maximum Pressure.
3 |  |  |  | Adjusted Maximum Pressure (AMP) exceeded |  | - Rate of pressure increase in IOW too quick for effective reaction time during an interwellbore communication event '- Inadequate well control plan for IOW | - Loss of barrier integrity in an IOW - Low relative value of Adjusted Maximum Pressure in relation to potential pressures from interwellbore communication (excessive well control plan and associate cost) | 1 | 1 |  | - Use pressure relieving system on IOW for the case where a relatively low Adjusted Maximum Pressure as compared to potential pressures from interwellbore communication - Stop fracture treatment on subject well and immediately relieve pressure on subject well
4 |  |  |  | Pressure integrity test conducted in the opposite direction of flow |  | - Inability to test a barrier in a direction of flow due to wellbore configuration / construction - Interwellbore communication flow path opposite direction to what was planned for | - Barriers may have lower pressure integrity in the direction of flow (e.g., cemented perforations, bridge plugs, downhole isolation devices, etc.) - Can not monitor pressure below a barrier in the direction of flow | 1 | 1 |  | - If high probability of interwellbore communication and concerns with a barrier's integrity in the direction of flow, consider adjusting the Subject Well's frac design to reduce the interwellbore communication probability. - Consider adding a secondary barrier on a flow path
5 |  |  |  | IOW barrier fails to groundwater |  | - An interwellbore communication event’s pressure exceeds a groundwater barrier’s integrity capacity - Annular hydraulic isolation is inadequate between interwellbore communication flow path and groundwater | - Age and/or operating history of well has reduced the integrity capacity of barrier(s) - Intermediate or production casing annulus cement top is below base of groundwater (not cemented to surface) and surface casing shoe is set shallower than base of groundwater - Cement squeezed shallow zone perforations lose their integrity or have lost their integrity - Interwellbore communication to a non-energy well (i.e. water well) - Creation of a surface casing vent flow - Contamination event is not detected and/or goes undetected - Radioactive substances used for tracing purposes on Subject Well migrate into aquifer | 1 | 1 |  | - Follow IRP 24 Hazard Management Process for Interwellbore Communication - Follow Directive XX (Hydraulic Fracturing); Non-saline Aquifer protection and Hydraulic fracturing near water wells sections. - Consider adding a secondary barrier to groundwater - Avoid radioactive tracers when groundwater has only a primary barrier with no secondary barrier back-up
6 |  |  |  | IOW is Abandoned (Cut & Capped) |  | - Assumed the abandoned IOW completed with regulatory standards at the time of the abandonment - Assumed service, age, & type of barriers in wellbore | - Not able to effectively monitor this type of IOW - Most likely only able to reduce risks at this type of IOW by adjusting the Subject Well's fracture stimulation plan - An interwellbore communication event is not detected and/or goes undetected - The abandon wellbore penetrates or terminates near the target zone - Can not integrity test or protect this type of IOW barriers - Abandonment barrier(s) inadequate to contain interwellbore communication pressures - Age & service of the abandoned wellbore can have a affect on barrier(s) integrity - Severity of consequences of an interwellbore communication event | 1 | 1 |  | - Extensively scrutinize IOW abandonment quality and zonal penetrations to assess risk and then adjust the Subject Well's fracture stimulation plan to reduce the likelihood of interwellbore to as low as reasonably practicable - Avoid having any abandoned wells within an FPZ
7 |  |  |  | Interwellbore communication to a subsurface object other than a wellbore (i.e., mineshaft, cave, non-energy wellbore, etc) |  | - Unknown subsurface feature within the FPZ - Object is in close proximity to Subject Well | - Damage or flooding of mine or cave - Injury to personnel involved with subsurface feature - Uncontrolled release to surface - Water well and/or aquifer compromised | 1 | 1 |  | - Identify and risk assess all known subsurface features within FPZ - Put a control plan in place to reduce and mitigate the risk of interwellbore communication to offset feature
8 |  |  |  | Inadequate hydraulic isolation in IOW |  | - Inadequate historical drilling practices (lack of standards used on old wells) - Problems while drilling (i.e. loss circulation) - Historic operational issues - Cement and casing degradation due to wellbore fluids - Cement and casing degradation due to high pressure injection history | - Interwellbore communication path and/or mechanism to an Other Zone above the Target Zone - Reduction in barrier integrity - Ground water contamination | 1 | 1 |  | - If high probability of interwellbore communication and concerns hydraulic isolation, consider adjusting the Subject Well's fracture initiating point and/or frac design to reduce the interwellbore communication probability. - Remedially repair IOW's hydraulic isolation integrity
9 |  |  |  | IOW active downhole drilling operation encounters unexpected high pore pressure gradient |  | - IOW has active downhole operations (see Section 24.2.3.4) - An IOW active drilling operation drills into a hydraulic fracture that has retained pressures from a Subject Well's fracture treatment (unexpectedly high pore pressure gradient) | - Well control incident on IOW active downhole drilling operation - Subject well fracture stimulation operational timing changed from original plan and/or notification, but now coincides with active downhole drilling operation | 1 | 1 |  | - As part of the notification process, continuously check operational timings for changes and assess IOW's with active downhole operations have become at-risk as a result of changes to operational timings. - Avoid active IOW drilling operations for a reasonable period of time following a Subject Well's fracture stimulation operation - Ensure the drilling plans are prepared for and consider the possibility of drilling into a hydraulic fracture that has retained fracture stimulation pressures
10 |  |  |  | IOW has sour zones and/or is producing sour fluids |  | - IOW has sour zones and/or is producing for a sour zone below the Subject Well target zone and an interwellbore communication comprises a well's integrity such that sour fluids can migrate | - Sour fluids communicating to Subject Well and/or an IOW that is not designed for handling sour fluids. | 1 | 1 |  | - Extensive risk assessment and barrier analysis for development of more comprehensive well control plans in the event of interwellbore communication
11 |  |  |  | Maximum pressure pulses at IOWs occur after the subject well frac pumping operations have shutdown (a delayed response) |  | - High pressure from subject well frac takes time to migrate through the reservoir to the IOW | - Monitoring and response action is planned for during the subject well frac operations, but this event can occur post frac when monitoring and response preparation is not in place. | 1 | 1 |  | - Area experience needs to be risk assessed for this type of reservoir response at an IOW
12
13
14

## Interwellbore
Item | Sub IRP | Category | Position | Hazard Scenario | Applicable | Cause How can this happen? | Threats / Consequences What events/incidents can result? | HSE | NPT | Required HSE Critical Controls / Safeguards | Industry Suggested Controls and Mitigations How can this be prevented? | Actions to be taken / By Who and When | Frequency of Exposure | Probability of Loss | Consequences | Risk Ranking | Operational Phase | Primary Responsible Party | Related to Item
1 | Other |  |  | Frac equipment refueling hose/line leaks | Y | - Hose/line failure due to fittings incorrectly installed - Hose/line not integrity tested prior to use - Fatigue failure of hose/line - Hose/line degradation due to lack of proper inspection process - Damage to fuel lines/hose from mobile equipment on wellsite | - Hose/line failure due to fittings incorrectly installed - Hose/line not integrity tested prior to use - Fatigue failure of hose/line - Hose/line degradation due to lack of proper inspection process - Damage to fuel lines/hose from mobile equipment on wellsite |  |  |  | -appropriate fire suppression on location (number of fire trucks for number of pumps)
2 | Other |  |  | Treating Line failure | Y | -Screenout, plugged line, frozen line, electronic failure, improper trip settings, relief valve failure, overpressure, washout, improper rig-in, miss-matched unions | - Fire and explosion - Harm to personnel - Lost time and cost - Damage to equipment |  |  | Pressure relief valve, | Pressure relief valve, iron mgmt and testing standards, rig-in standards (sufficient flexibility, tie-downs, flow capacity etc), flowback requirements, no personnel in high pressure zone
3 | Other |  |  | Chemical Spill | Y | -Valve failure, rupture of tote, line failure, washout, seal failure | Environmental, harm to personnel, lost time and cost |  |  | - PPE, fire suppression equipment, containment in chem vans, shower units | - Control toxicity of chemicals being used/chemical substitution, visual inspection of chem add hoses, stainless steel fittings (engineering controls), spill kits and training, order of addition for chemicals
4 | Other |  |  | Fire in chem van | Y | -release of low flash point chemical, use of alcohol to suppress freeze point, frozen chem add line, mixture of incompatible products | -Environment, harm to personnel, fire, damage to equipment |  |  | - PPE, fire suppression equipment, containment in chem vans, shower units | -Standards for chem add packages in specific environments, standards for segregation of products during transport
5 | Other |  |  | Well control failure at wellhead | Y | Wellhead component failure, treating line failure, testing equipment failure, overpressure, washout, communication with offsetting well | - Fire and explosion - Harm to personnel - Lost time and cost - Damage to equipment |  |  |  | - Remote operated wellhead valve, redundant wellhead valves, treesaver, properly configured wellhead stacks (large enough ports/connections)
6 | Other |  |  | CO2/N2 release | Y | -Suction hose failure, containment vessel failure, treating line failure | Harm to personnel, damage to equipment |  |  | Proper venting/relief valves on tanks, iron & hose testing/standards | -Standard for tank bleedoff at end of job
7 | Other |  |  | Packing failure | Y | Improper maintenance, improper packing, wrong packing material, inadequate lubrication | - Fire and explosion - Harm to personnel - Lost time and cost - Damage to equipment |  |  | Maintenance standards, training, Pump ESD's | -Head tarps, pump covers
8 | Simultaneous Operations |  |  | Concurrent operation | Y | Small leases, multiple wells per lease, efficiency |  |  |  |  | -Wellhead spacing regulations, consideration for acceptable simultaneous ops, egress plans
9 | Other |  |  | Pumping recirculated fluids | Y |  | H2S exposure, flammability, damage to equipment/treating iron, unknown contaminants (required PPE) |  |  |  | -standard for frac water, MSDS requirement, minimum sampling and testing requirements
10 | Other |  |  | Prolonged exposure to silica sand | Y | Larger fracs and multiple zones require in the multiple of 10 times the volume of sand | Exposure above the OEL to workers of Silica sand |  |  | Increased PPE respiratory protection | Exposure monitoring, and health assessment monitoring.
11 | Other |  |  | High pressure frac line failure clean side | Y | water cannon effect
12 | Other |  |  | High pressure frac line failure dirty side | Y | cannon effective containing possible corrosives or sand
13 | Other |  |  | High pressure frac union or fitting failure | Y | both clean and dirty side
14 | Other |  |  | Ice plugs or hydrates forming in frac line | Y
15 | Other |  |  | High pressure lines whipping around following a failure or separation | Y
16 | Other |  |  | Chemical or corrosive release high volume/low volume | Y
17 | Other |  |  | Vapour release high volume or low volume, high pressure and low pressure (propane frac) | Y
18 | Other |  |  | The special case of hydraulic fracture stimulating in shallow wells, particularly those at target depths less than 600 m or within 300 m of the base of groundwater protection is cause for concern and very careful evaluations are required. | Y
E.g. |  |  |  | FPZ is Underestimated |  | - See Appendix A of IRP 24 document - Geology - Inadequate Modeling - Fracture Treatment Larger than planned - Multiple stages pumped into one stage unintentionally (inadequate stage isolation, frac goes only into one perforated interval on a multi-perforated stage, longitudinal frac, hz pancake frac) - Fracture Treatment type change from plan - Intersection of offset hydraulically fractured wellbores - FPZ reservoir depletion | - Loss of barrier integrity in an IOW - Unintentional interwellbore communication - Fault(s) can considerably extend fracture half length, thus increasing the likelihood of interwellbore communication to wells within the FPZ and beyond the FPZ (i.e., a fault can create FPZ estimation uncertainty) '- Packer or cement failing to isolate frac into desired interval - Ball activated system failure (ball not dropped, ball fails, downhole seat fails). Wrong ball dropped on sleeve. Extra ball in system accidentally left over from another well's frac operation - Friction diversion not working for limited entry frac - Seat is worn on ball/seat job so ball does not shift sleeve - Coil fraccing downhole isolation packer/tool fails and bypasses to previously fracced stages below it | 1 | 1 |  | - If faulting is anticipated, establish IOW well control plans based on a higher likelihood of interwellbore communication - Compile area experience for more accurate FPZ determination - Consider adding a fault related safety factor to intentionally expand the FPZ - If faulting is anticipated, consider all possible SCW's as at-risk - Micro-seismic to asses frac propagation behaviour when perforating multiple intervals for a single frac stage | [8 empty] | 1

## Surface Operations
Item | Sub IRP | Category | Position | Hazard Scenario What is existing? | Applicable | Cause How can this happen? | Threats / Consequences What events/incidents can result? | HSE | NPT | Required HSE Critical Controls / Safeguards | Industry Suggested Controls and Mitigations How can this be prevented? | Actions to be taken / By Who and When | Frequency of Exposure | Probability of Loss | Consequences | Risk Ranking | Operational Phase | Primary Responsible Party | Related to Item
E.g. |  |  |  | vehicular collisions |  | poor roads (icy), inexperienced drivers, congested locations, excessive traffic, worker incompetency | injury to people, damage to equipment, property, environment | 1 | 1 |  | follow hours of service, use of land guides, driver training and mentorship programs, barriers, traffic controllers

## Well Barrier Diagram - Oil Well (hidden)
Subject Well Barrier Schematic | [8 empty] | Date:
Well Name / UWI:
Location:
|  |  |  | Status: | Producing
[9 empty] | OEM | Adjusted
| Subject Well | [6 empty] | Barriers | Spec | Max Pressure
[9 empty] | (MPa) | (MPa)
[8 empty] | 1. Wellhead | 21 | 18
|  |  |  | 1 |  |  |  | 2. Tubing spool | 21 | 18
[8 empty] | 3. Surface casing | 4 | 4
[8 empty] | 4. Surface casing cement/annulus | untested | untested
|  |  | 2 |  |  |  |  | 5. Production casing | 32 | 21
[8 empty] | 6. Production casing cement / annulus | untested | untested
[8 empty] | 7. Liner* | n/a | n/a
[8 empty] | 8. Liner cement / annulus* | n/a | n/a
|  | 3 | [5 empty] | 9. Tubing* | 55 | 50
[8 empty] | 10. Packer* | 42 | 40
| 4 | [6 empty] | * if applicable
| 400m | [5 empty] | BGWP
| 500m | [5 empty] | Casing Shoe
|  | 750m |  |  |  | Cement Top
5
6
9
10
1800m
TARGET
ZONE
1900m

## Well Barrier Diagram - Inj Well (hidden)
Well Barrier Schematic | [12 empty] | Date:
Well Name / UWI:
Location:
[5 empty] | Status: | Wateflood Injection
* O = Open, C = Closed
[13 empty] | OEM | Adjusted | Barrier | IOW
| Existing Waterflood Injection Well | [10 empty] | Barriers | Capacity | Max Pressure | Status | Monitored
[13 empty] | (MPa) | (MPa) | *(O / C) | (Y / N)
Primary Dependent
Barrier System
[12 empty] | 1. Wellhead valve | 21 |  | C
[12 empty] | 2. Flowline tee | 21 |  | C
[12 empty] | 3. Tubing hanger seals | 21 |  | C
[5 empty] | 1 |  | 6 |  |  |  |  | 4. Prod casing head valves (a,b) | 21 |  | C
[5 empty] | 2 |  |  |  |  | 5 |  | 5. Flowline valve | 21 |  | C
[5 empty] | A | [6 empty] | 6. Flowline | 21 |  | C
3
Secondary Dependent
| 4a | [8 empty] | 4b |  | Barrier System
[8 empty] | C |  |  |  | A. Wellhead master valve | 21 |  | O
|  |  | F | [7 empty] | B | B. Surface casing vent valve | 3.5 |  | C
[5 empty] | G | [6 empty] | C. Prod casing hanger seals | 21 |  | C
[12 empty] | D. Prod casing cement / annulus | untested |  | C
[12 empty] | E. Surface Casing Shoe | 3.6 |  | C
(18 kPa/m frac gradient)
[9 empty] | E |  |  | F. Surface Casing | 3.6 |  | C
|  | 200m | [6 empty] | Casing Shoe |  |  | G. Prod casing (burst) | 28 |  | C
|  |  | 400m |  |  |  |  | BGWP
|  |  | 750m |  |  |  |  | Cement Top
D
1800m
EOR INJ
ZONE

## Introduction (2) (hidden)
IRP 24 Hazard Register
Column Headings
Column Letter
Item | A | Sequential item number for hazards in each operational phase.
Hazard Scenario What If | B | Single jeopardy statement used to identify potential problems due to failure in pre-job planning, training, procedures, or equipment failure.
Applicable | C | Choose "Y" if "Hazard Scenario What If" applies to operation and "N" if it does not.
Threats/Consequences | D | A list of the potential consequences (HSE and NPT) of the "what if" occurring.
HSE | E | The risk of a situation/event with the potential to cause harm (to people, assets, or the environment).
NPT | F | The risk of Non Productive Time (NPT), including lost time and costs, formation damage and/or any deviation from the plan.
Required HSE Critical Controls / Safeguards | G | Controls/safeguards, and detailed recommended practices for high risk HSE items and referenced to specific prescriptive IRP 24 enforced requirements.
Considerations | H | Recommendations, considerations, and informational statements on how to reduce, eliminate, or manage Medium/Low Risk HSE items and all NPT items.
Actions to be Taken / By Who and When | I | List of actions required to reduce/eliminate the potential occurrence and/or severity if the hazard cannot be eliminated entirely. Who = Party/parties responsible for each action assigned. When = Date by which the action is to be completed.
Operational Phase | J | Categorization of the hazard scenario by operational phase.
Primary Responsible Party | K | Categorization of the hazard scenario by primary responsible party.
Primary Category | L | Categorization of the hazard scenario by primary category (equipment, well program, etc.)
Risk Ranking - severity of the event (consequence multiplied by likelihood of occurrence)
1 |  | High Risk - Engineering, Procedures, and Training required to control/mitigate risk.
2 |  | Medium Risk - Procedures and Training required to control/mitigate risk. Should consider Engineering.
3 |  | Low Risk - Training required to control/mitigate risk. Should consider Engineering and Procedures.
General Notes about Register