## The Plan
The "Are You in the Line of Fire?" Program Project Execution Plan | time axis 2016-02-01 to 2016-05-09
Required Outcome | Actions | Specific Deliverable | Draft | Team | Translation | Hyperlink (OLL) | Hyperlink (LL) | Type of Document | Comments | Package | Priority | bar: 2016-02-11; 2016-02-18; 2016-02-28; 2016-03-03; 2016-03-11; 2016-03-17; 2016-03-20; 2016-03-24; 2016-04-01; 2016-04-08; 2016-04-16; 2016-05-04
Translation of all applicable material that support the Line of Fire Injury Reduction Program | 1) Line of Fire - Leadership Alignment
2) General Communications
3) Supporting Documents
4) Supporting Documents (General)
5) Supporting Documents (Activity 1) Stored Energy
6) Supporting Documents (Activity 2) Striking Hazard
7) Supporting Documents (Activity 3) Crushing Hazard
8) Sustainment