## Intro Sheet
IRP 22 Hazard and Risk Assessment Register
Column Headings
Column Letter
Operational Phase | A | Categorization of the hazard scenario by operational phase.
Item | B | Item number for hazards.
UBD/MPD/RMD/All | C | Identification of whether the hazard applies to UBD, MPD, RMD, a combination of two or all
Hazard Scenario What If | D | Single jeopardy statement used to identify potential problems due to failure in pre-job planning, training, procedures, or equipment failure.
Applicable | E | Choose "Y" if "Hazard Scenario What If" applies to operation and "N" if it does not.
Threats/Consequences | F | A list of the potential consequences (HSE and NPT) of the "what if" occurring.
HSE | G | The risk of a situation/event with the potential to cause harm (to people, assets, or the environment).
NPT | H | The risk of Non Productive Time (NPT), including lost time and costs, formation damage and/or any deviation from the plan.
Required HSE Critical Controls / Safeguards | O | Controls/safeguards, and detailed recommended practices for high risk HSE items and referenced to specific prescriptive IRP 22 enforced requirements.
Considerations | J | Recommendations, considerations, and informational statements on how to reduce, eliminate, or manage Medium/Low Risk HSE items and all NPT items.
Actions to be Taken / By Who and When | K | List of actions required to reduce/eliminate the potential occurrence and/or severity if the hazard cannot be eliminated entirely. Who = Party/parties responsible for each action assigned. When = Date by which the action is to be completed.
Primary Responsible Party | L | Categorization of the hazard scenario by primary responsible party.
Primary Category | M | Categorization of the hazard scenario by primary category (equipment, well program, etc.)
Risk Ranking - severity of the event (consequence multiplied by likelihood of occurrence)
1 |  | High Risk - Engineering, Procedures, and Training required to control/mitigate risk.
2 |  | Medium Risk - Procedures and Training required to control/mitigate risk. Should consider Engineering.
3 |  | Low Risk - Training required to control/mitigate risk. Should consider Engineering and Procedures.
General Notes about Register
Register is divided into two sheets - MAIN for RMD/MPD/UBD specific risks and GENERAL for general drilling risks.
Register is divided into 8 sections, coinciding with the operational phases of RMD/MPD/UBD operations.
Additional items may be added to each section by the IRP committee or the end user. The list of items in the register is not exhaustive and will change with time as additional hazards are identified. Last item number used (as of 2019-11-21) is: 243 Begin any additional numbering with 245. Note that #152 was deleted as it was redundant.
The IRP 22 Committee invites organizations to share lessons learned and additions to the Risk Register via the IRP 22 Risk Register Update Form available on the IRP 22 landing page on the Energy Safety Canada website (www.energysafetycanada.com).
Use alt+enter to create multiple line items within a single cell
Validations of operational phase, relevance, primary responsible party, primary category and y/n columns use the data in the tabs mathcing their name. All validations are set up to validate any value from the entire column so when adding a new item it will automatically be included in the validation.
To subscript for H2S, O2, N2 etc, select the character to subscript, right click and choose format cells, check off subscript
Risk Register is set up to print on LEGAL paper in landscape layout.

## Hazard Register MAIN
Operational Phase | Item | Relevance | Hazard Scenario What If ? | Applicable | Threats/Consequences | HSE | NPT | Required HSE Critical Controls / Safeguards | Considerations | Actions to be taken / By Who and When | Primary Responsible Party | Primary Category
1. Planning | 5 | ALL | Improper separator - too small | Y | Fluid carryover may cause a fire, environmental damage/injury. Wait on right size equipment. | 1 | 1 | 22.7.2 22.7.3 22.7.7 22.4.5 22.4.6 22.12.5 | Conduct review with reservoir/production engineers regarding potential inflow rates. Review separator sizing requirements with service company. |  | UBD/MPD/RMD Service Provider | Separation
1. Planning | 6 | ALL | Threaded unions are used in high pressure pipe work. | Y | Poor quality control in NPT thread design/manufacture may result in flowline failure. | 1 | 1 | 22.12.1 References | No threaded unions to be used for other than shipping lines. |  | UBD/MPD/RMD Service Provider | Choke/Flowline
1. Planning | 7 | GAS INJECTION OPS (UBD/MPD) | Membrane nitrogen is used in sour environment | Y | High corrosion rate. Potential flammable conditions. | 1 | 1 | 22.4.10 22.7.7.4 Appendix D | Consider use of service gas that does not contain oxygen. |  | Operating Company | Well Program
1. Planning | 8 | ALL | Condensate carryover | Y | Spill - environmental damage Start fire in immediate vicinity | 1 | 1 | 22.7.2 22.7.3 22.7.7 22.4.5 22.4.6 22.12.5 | Choose appropriately sized separator for flush production. Review procedures for transient operations (such as initial blowdown). |  | Operating Company | Well Program
1. Planning | 9 | ALL | Failure to flush/purge lines, vessels, surface equipment | Y | H2S exposure to personnel. Low volume, high concentration. Potential for injury/death. | 1 | 1 | 22.7.6 22.7.7 22.12.5 22.16 | Purge with an inert gas. |  | UBD/MPD/RMD Service Provider | Separation
1. Planning | 10 | ALL | Barrier Failure | Y | Loss of barrier. Potential for injury/death. | 1 | 1 | 22.5.1 22.8.3 | Consider 2 barriers when pipe is static. High H2S content should make barrier policy more visible. |  | Operating Company | Well Program
1. Planning | 12 | GAS INJECTION OPS (UBD/MPD) | General H2S concerns | Y | Potential for injury/death. | 1 | 1 | 22.4.5.5 22.4.6 22.6.4 | Equipment spacing, venting and issues regarding personnel safety must be addressed throughout the entire lease for the entire operation. |  | Operating Company | Lease Management
1. Planning | 13 | AIR DRILLING | Air Drilling - LEL and UEL within flammable limits | Y | Flammable mixture, potential for fire/explosion. | 1 | 1 | 22.7.7 22.17.1 | Eliminate one element of the requirements for combustion (fuel, oxygen, or ignition source). Consider inert gas operations. Never flow returns to a closed separator. Add inert gas to reduce flammability. |  | Operating Company | Well Program
1. Planning | 14 | AIR DRILLING | Air Drilling - Unexpected hydrocarbon zone encountered | Y | Potential for downhole fire and/or ignition at surface. | 1 | 1 | 22.7.7 22.17.1 | Use inert gas if the risk of creating conditions suitable for combustion exists. Consider inert gas operations. |  | Operating Company | Well Program
1. Planning | 15 | AIR DRILLING | Air Drilling - Mud ring occurs with combustible mixture in hole. | Y | Potential for downhole ignition. Loss of BHA, damage to equipment, potential for injury/death, loss of well. | 1 | 1 | 22.7.7 22.17.1 | Monitor hole cleaning and fluid influx carefully while drilling. Consider inert gas operations. Section 22.17.1 doesn't exist. |  | Operating Company | Well Program
1. Planning | 19 | ALL | Inadequately vented "closed" atmospheric tanks. | Y | Pressure build up in atmospheric tanks due to high liquid flow rate or high solution gas content leading to possible tank rupture, personnel injury or environmental spill. | 1 | 1 |  | Ensure installation design considers maximum input rates to closed atmospheric tanks and sufficiently sized vent lines are provided. |  | UBD/MPD/RMD Service Provider | Choke/Flowline
1. Planning | 21 | ALL | Failure to note losses, possibly leading to loss/kick situation | Y | Possible inadequate returns monitoring and/or flow modeling fails to recognize losses in zone of greater depletion/lower pore pressure than planned for. Possibility of well kick exceeding equipment rating, personnel injury, equipment damage or loss of well. | 1 | 1 | 22.4.3 | Ensure adequate monitoring, early recognition of losses, well planned well control procedures. Consider fluid system. E.g., foaming issues with various mud systems/additives. |  | Rig Contractor | Mud System
1. Planning | 22 | ALL | High temperature (i.e. HPHT wells) exceeding BOP seals temperature rating | Y | HPHT wells surface temperature exceeding BOP, etc. temperature rating leading to premature failure, loss of containment, personnel injury, loss of well control. | 1 | 1 | 22.4.2 22.4.8 22.10.6 | For HPHT wells consider use of additional temperature monitoring and ESD procedures for Temperature HH conditions at BOP stack. Use proper sealing rubber for high temperature. |  | Operating Company | BOP System
1. Planning | 23 | ALL | Ported floats are used | Y | Pressure communicated to surface through drill pipe. Cannot hold back pressure on annulus as pressure is communicated to surface through drill pipe. | 1 | 2 | 22.12 22.18.4 | Use 2 non-ported float valves. Run NRV as contingency for drop-in check valve. |  | NRV Supplier | NRV
1. Planning | 24 | ALL | Unclear lines of authority | Y | Risk to personnel, equipment, environment. | 1 | 2 | 22.15.3 | All lines of authority to be clearly defined in program/pre-spud. |  | Operating Company | Well Program
1. Planning | 29 | ALL | H2S - Toxic gas released during cuttings separation process. | Y | Potential for injury/death. | 1 | 2 | 22.4.5.6 | Use enclosed cutting separation process. Vacuum degas fluid/solids stream before cuttings separation. Monitor/alarm any area where there is a potential for a sour gas release. |  | UBD/MPD/RMD Service Provider | Separation
1. Planning | 30 | UBD/MPD | H2S - Toxic gas released from fluid storage system. | Y | Potential for injury/death. | 1 | 2 | 22.4.5.6 | Use enclosed fluid separation process. Vent tanks through scrubbers. Monitor/alarm any area where there is a potential for a sour gas release from the fluid storage system. |  | UBD/MPD/RMD Service Provider | Separation
1. Planning | 31 | UBD/MPD | H2S - Toxic gas release when sampling cuttings | Y | Potential for injury/death. | 1 | 2 | 22.4.3 22.4.5.6 | Purge with non-toxic or inert gas before opening sampler. |  | UBD/MPD/RMD Service Provider | Separation
1. Planning | 32 | UBD/MPD | H2S - Improper sour service material selection | Y | Rapid degradation of steel - not fit for service. | 1 | 2 | 22.4.5.6 | Full review of NACE MR 0175/ISO 15156 for H2S wells. Review IRP 1 Critical Sour Drilling |  | Operating Company | Well Program
1. Planning | 33 | ALL | Oil Based Mud - Solution gas release from drilling mud | Y | Risk of fire/explosion and personnel exposed to harmful vapors. | 1 | 2 | 22.16.3 22.4.5.6 | Calculate volume of gas released from separator pressure to atmospheric pressure. Low pressure separator reduces gas in solution. Use separate fluid storage system with totally enclosed and vented tanks. |  | UBD/MPD/RMD Service Provider | Separation
1. Planning | 35 | ALL | H2S - Elastomer failure/incompatibility | Y | Loss of Barrier. Potential for injury/death. | 1 | 3 | 22.4.5.6 | Aniline testing elastomers. Proper material selection for elastomers. |  | Operating Company | Well Program
1. Planning | 36 | ALL | Shortage of experienced people in planning stages | Y | Inability to identify all safety critical issues in the operation. | 2 | 1 |  | Ensure that personnel planning the operation are competent to do so. |  | All | N/A
1. Planning | 38 | ALL | BHA plan includes running spiral drill collars or other non-strippable components. | Y | RCD leakage. Injury to personnel. Unable to strip through RCD element. Delay in drilling well (lost time and cost). | 2 | 1 |  | May only be consideration if planning to strip BHA through RCD. Review all drill sting components for strippability and sealability with the RCD. Spiral drill collars, jars, bumper subs and stabilizers are not recommended. Function/stripping tests of odd-profile BHA components (on and/or offsite) is recommended. Avoid use of kelly valves with rubber casing savers. Replace spiral DC with Rigid DC or HWDP. |  | Operating Company | Drill String
1. Planning | 40 | ALL | Crew shortage and/or inexperience | Y | Harm to personnel. Lost time and cost. | 2 | 1 | 22.9 Appendix H | Onsite orientation and training. Supervisors to ensure that all personnel have been trained in the various components of the rig up operation. Identify tasks in tool box safety meetings. Ensure all workers understand their right to refuse unsafe work, or request training/guidance for tasks that they are not yet competent in. Consider EMS onsite during rig up operations. Focus on shift change communication information transfer. Check IRP 22.16.3 Operational Communications |  | All | N/A
1. Planning | 41 | UBD/MPD | NRV seal compatibility with fluid | Y | Potential for NRV to fail prematurely. | 2 | 1 | IRP21 | Consider multiple NRVs in BHA. Consider metal/metal seals. Test seals with drilling fluid/reservoir fluid prior to drilling operation. Consider profile nipple down hole as a backup. |  | NRV Supplier | NRV
1. Planning | 43 | UBD | High Rate Flaring | Y | Exceed volume limits, shut in well, cease operations. | 2 | 1 |  | High Productivity Index well probability, apply a suitable safety factor to modeling, calculations and permit applications. AER Directive 60: Upstream Petroleum Industry Flaring, Incinerating, and Venting (see www.aer.ca) |  | Operating Company / UBD/MPD/RMD Service Provider | Well Program
1. Planning | 44 | UBD | High H2S Flaring | Y | Exceed allowable limits for SO2 - 172 ppb/volume. Shut in well, cease operations. | 2 | 1 |  | Gas Chromatograph to qualify modeling. Continuous H2S content monitoring in fluid stream. AER Directive 60: Upstream Petroleum Industry Flaring, Incinerating, and Venting (see www.aer.ca) |  | Operating Company | Well Program
1. Planning | 51 | ALL | Separator liquid carry-over into flare line and/or shipping pump failure | Y | Spill - environmental damage Fire, explosion from flare stack, personnel exposure Separator over-pressure | 1 | 2 | 22.7.7 | Cold venting (regulatory exemption may be required). Automatic liquid high level shut-down in separator. Flare stack spacing, height and ground clearance from combustible materials. Procedures and equipment in place for managing separator level if level no high level shut-down. Audible and visual alarm. Ensure adequate redundancy of pressure shipping and pump shipping capacity. |  | UBD/MPD/RMD Service Provider | Separation
1. Planning | 52 | ALL | Separator gas carry-under down the liquid shipping lines | Y | Gas at rig tanks. Fire, explosion, personnel exposure. | 1 | 2 | 22.7.7 | Automatic liquid low level shut-down in separator. Procedures and equipment in place for managing separator level if level no low level shut-down. Audible and visual alarm. LEL/UEL gas monitoring and alarming at the shaker Liquid shipping to a remote tank system. |  | UBD/MPD/RMD Service Provider | Separation
1. Planning | 53 | ALL | Trying to flare with high CO2 mol% | Y | No burn - cold vent. | 2 | 2 |  | Use of supplementary fuel gas (Propane). AER Directive 60: Upstream Petroleum Industry Flaring, Incinerating, and Venting (see www.aer.ca) |  | Operating Company | Well Program
1. Planning | 54 | ALL | Oil Based Mud - Increased solubility in oil based mud (GOR variability) | Y | Poor H2S Stripping / Separation. Potential for injury/death. | 2 | 2 |  |  |  | UBD/MPD/RMD Service Provider | Separation
1. Planning | 58 | ALL | RCD doesn’t fit under sub | Y | Attempts to try and fit RCD could cause injury to personnel. Can not drill UBD/MPD. Delay in drilling well (lost time and cost). | 3 | 1 |  | Raise/lower rig sub height and/or casing bowl. Verify and check equalizing line clearance if built too high. Change BOP equipment. Use different rig. Use different RCD. Add pony sub under rig. RCD supplier to go to location to check out rig's sub prior to job. Accurate BOP stack-up and rig substructure clearance measurements |  | RCD Supplier | RCD
1. Planning | 60 | AIR DRILLING | Air Drilling - Water influx is encountered | Y | Hole cleaning problems, delay in operation. | 3 | 1 |  | Operational plan should include contingency for switching to mist, foam and mud operations. |  | Operating Company | Well Program
1. Planning | 61 | ALL | Drill pipe and/or tool joint size different than planned | Y | Premature RCD element wear. Wrong size RCD stripper elements on location. Delay in drilling well (lost time and cost). RCD fails to pressure test. | 3 | 2 |  | Drill string inspection. Verify drill string size. RCD supplier SOPs/risk register. Drill string diagram. |  | Operating Company | Drill String
1. Planning | 68 | UBD | Flush Liquid Production | Y | Exceed separator throughput capacity. Release of burning oil/condensate from flare tip. | 3 |  |  | High Productivity Index well probability, build some 'fat' into modeling, calculations, and permit applications. |  | Operating Company | Well Program
2. Rig Up / Pressure Test / Commissioning | 81 | ALL | Well parameters different from program - PRESSURE | Y | Surface equipment may not be suitable in terms of pressure rating/flow rate capability - wait on equipment. Fluid system may not be capable of achieving required pressure profile. | 2 | 1 |  | Offsets to be analyzed as a guide for planning the operation. Assume worst-case scenario when planning the well. Consider flush-production scenario encountered in UBD operations. |  | Operating Company / UBD/MPD/RMD Service Provider | Well Program
2. Rig Up / Pressure Test / Commissioning | 82 | UBD/MPD | Failure to install check valve on each injection line | Y | Possibly pressurize mud pump system through nitrogen injection line (suction line may fail). Gas lock mud pump. | 2 | 1 |  | Discuss requirements in pre-spud. Check valve to be installed downstream of all pumping equipment in operations using a service gas. |  | Operating Company / UBD/MPD/RMD Service Provider | Compression
2. Rig Up / Pressure Test / Commissioning | 83 | ALL | Well parameters different from program - H2S | Y | Surface equipment may not be suitable for handling sour fluid. Additional concerns with regards to HSE for safe operations, fluid transportation, etc. | 2 | 1 |  | Offsets to be analyzed as a guide for planning the operation. Assume worst-case scenario when planning the well. Plan for sour operations if there is even a small potential of encountering sour gas. |  | Operating Company | Well Program
2. Rig Up / Pressure Test / Commissioning | 87 | UBD/MPD | NRVs fail to pressure test or no documentation of pressure test | Y | Failure to pressure test increases likelihood of a leaking NRV occurring. | 3 | 1 |  | Paperwork with NRVs to include documentation of shop pressure test.. Consider onsite pressure testing apparatus. Have contingency procedures. Have spare(s) NRV available. |  | NRV Supplier | NRV
3. Drill Out and Hole Conditioning | 89 | ALL | Rig crews unfamiliar with process | Y | Harm to personnel, equipment or environment. Lost time and cost. | 1 | 1 | 22.7 | Detailed UBD/MPD program in place. Written procedures for critical operations available on rig floor. Review procedures with all personnel in a safety meeting before drillout. Consider dry run for critical procedures prior to drilling out. |  | Operating Company / UBD/MPD/RMD Service Provider | Training
3. Drill Out and Hole Conditioning | 90 | ALL | Valves incorrectly positioned on stack or manifold | Y | Possible overpressure of RCD or manifold at surface. Possible fluid release to atmosphere/environment. | 1 | 1 | 22.7 22.15.2 | Process flow diagram posted in dog house. Walk the pump lines before commencing drillout procedure. Consider labeling all valves and marking them as normally open or normally closed. All well control piping to be blown dry and/or heated to prevent freezing. |  | UBD/MPD/RMD Service Provider | Choke/Flowline
3. Drill Out and Hole Conditioning | 91 | ALL | Separator not purged prior to lighting flare | Y | Potential backflash/explosion in separation equipment. | 1 | 1 | 22.4.8 | Purge with nitrogen prior to lighting flare. Ensure backpressure system is operable on pressurized separator before lighting flare. |  | UBD/MPD/RMD Service Provider | Flare/Vent System
3. Drill Out and Hole Conditioning | 92 | ALL | Poor communications /unfamiliarity during well conditioning | Y | Overpressure at surface, dead-heading pumps and other HSE concerns. | 1 | 2 | 22.15.3 | Ensure hand signals are in place for important communications. Establish radio protocol in safety meeting. Supply sufficient head sets for men working in high-noise environments. Review roles in safety meeting. |  | Operating Company | Lease Management
3. Drill Out and Hole Conditioning | 93 | GAS INJECTION OPS (UBD/MPD) | Chemical injection pumps are not working or not calibrated. | Y | Risks of carryover from separator (environmental concern). Corrosion concerns. | 2 | 2 |  | Test injection pumps during rig up and commissioning. Store chemicals as per manufacturers recommendations. Consider connecting injection pumps to data system. |  | UBD/MPD Service Provider | Mud System
3. Drill Out and Hole Conditioning | 94 | UBD | Poorly designed hole conditioning procedure | Y | Excessive slugging and/or surface pressure and flow rates. Possible fluid carryover. | 2 | 2 |  | Detailed UBD program in place, including pump schedule. Written procedure in doghouse/UBD control unit. Procedure reviewed by engineering and discussed in safety meeting. |  | Operating Company | Well Program
3. Drill Out and Hole Conditioning | 95 | ALL | Data system not functioning properly | Y | Inability to react in real-time to well conditioning events. Possible errors in implementing hole conditioning pump schedule. | 2 | 2 |  | Test sensors and data system during commissioning phase and confirm operation prior to drillout. Ensure sensors are heat traced so that they don't freeze and provide erroneous data. |  | UBD/MPD/RMD Service Provider | Data Acquisition
3. Drill Out and Hole Conditioning | 96 | UBD/MPD | Formation integrity test insufficient for planned operations | Y | Unable to apply UBD/ MPD program. Possible well control concerns, lost time or harm to personnel. | 2 | 2 |  | May require additional casing string or redesign of MPD/UBD operation. Remedial cement job/re-drill and test. |  | Operating Company | Well Program
3. Drill Out and Hole Conditioning | 99 | GAS INJECTION OPS (UBD/MPD) | NRV not installed near surface prior to conditioning with compressible fluid | Y | Excessive bleed-off time/connection time. Possibly require re-conditioning hole after long bleed-off time to install NRV. | 3 | 2 |  | Reference and review drill string diagram. Discuss in safety meeting and confirm installation visually before commencing operations. Add drill string floats. |  | Operating Company / UBD Service Provider | NRV
4. Drilling | 100 | ALL | No strategy for "planned" shut downs | Y | Failure to consider the shutdown sequence may result in hole problems, high pressures at surface, unnecessary well kill, etc. | 1 | 1 | 22.16.1 | Add contingency plans. |  | Operating Company / UBD/MPD/RMD Service Provider | Well Program
4. Drilling | 101 | ALL | No strategy for "unplanned" shut downs | Y | Failure to consider the shutdown sequence may result in hole problems, high pressures at surface, unnecessary well kill, etc. | 1 | 1 | 22.16.1 | Add contingency plans. |  | Operating Company / UBD/MPD/RMD Service Provider | Well Program
4. Drilling | 102 | ALL | Separator fails | Y | Gas release and harm to personnel/environment. | 1 | 1 | 22.4.6 22.12.5 | Separation equipment certification must be current. PSVs installed and relief lines rigged up. Rig's well control equipment rigged in and operational in case of catastrophic failure. |  | UBD/MPD/RMD Service Provider | Separation
4. Drilling | 103 | ALL | Dead legs/liquid traps on permanently piped skid equipment - increased incidence of internal corrosion, leak and/or rupture | Y | Skidded equipment with permanent piping installations often incorporate pipe dead legs or liquid traps (i.e. concentric reducers instead of eccentric reducers) where acidic or corrosive liquids accumulate and are not easily flushed. Possible leak or rupture with resultant personnel, equipment and environmental consequences. | 1 | 1 |  | Consider inspection of skidded equipment permanent piping for dead legs and liquid traps and remove or provide means of inspection and documentation. |  | UBD/MPD/RMD Service Provider | Separation
4. Drilling | 104 | ALL | Washout occurs on primary flowline from BOP stack to the separation equipment | Y | Gas release on location. Personnel injury. Damage to equipment. | 1 | 1 | 22.16 | Consider onsite Ultrasonic Thickness (UT) monitoring program. Maximize separator pressure to minimize velocity in flow line. Service company to provide erosion management document. Operate within Operations Matrix parameters. Train on critical operations such as shutting in or diverting to secondary flowline or equalizing line. Maintain flow velocities in primary flowline below (55 m/sec) in absence of detailed erosion modeling. Reduce number of flowline turns. Ensure 10 internal diameters spacing between flowline turns. This allows the flow to straighten prior to the next turn. Primary flowline must contain targeted tees (turns) and be a minimum 101.6 mm in outside diameter or larger. Maximize liquid injection rate. |  | UBD/MPD/RMD Service Provider | Well Program
4. Drilling | 105 | UBD/MPD | Pipe wall thickness erosion | Y | Over time pipe wall erodes or corrodes leading to reduction in pressure integrity, possible leak or rupture with resultant personnel, equipment and environmental consequences. | 1 | 1 | 22.10 22.12 | Implement pipe inspection procedures and documentation prior to each rig up, and NDT wall thickness inspections at vulnerable points throughout operation. UT testing when possible. Refer to API Standards. |  | UBD/MPD/RMD Service Provider | Separation
4. Drilling | 106 | ALL | RCD drill string sealing element failure or RCD Control Unit Failure | Y | Gas/Hydrocarbon fluid release at rig floor. Ignition and explosion risk. Possible formation damage if well has to be killed. | 1 | 1 | 22.11.3 22.14.3 22.16.1 | Check rig alignment before and during operation. Monitor RCD performance while drilling. Replace elements as per supplier's SOPs before major leakage occurs. Have a backup element ready for quick installation. Consider installing a new element during low risk times (out of hole, prior to starting drilling after a trip, etc.). Complete regular inspection of the control unit and its operability. Indication of failure is to be considered a well control event. Consider a redundant back-up unit onsite. |  | RCD Supplier | RCD
4. Drilling | 107 | ALL | No procedures in place for replacing RCD element | Y | Improperly attempting to change the RCD element may result in fires, explosions or other catastrophic HSE events. Harm to personnel. | 1 | 1 | 22.12 22.16.1 | Reference supplier's SOPs for changing the RCD element. Rehearse equalizing procedure prior to conducting operations. Back pressure required during process. |  | RCD Supplier | RCD
4. Drilling | 108 | ALL | RCD element deteriorates | Y | Choke plugging, equipment damage. Compromise of well control barrier. | 1 | 1 | 22.12 22.16.1 | Reference supplier's SOPs for the use and maintenance of the RCD. Have bearing/rubbers available. |  | RCD Supplier | RCD
4. Drilling | 111 | ALL | Circulating through flexible hoses/shock hose | Y | Failure of hoses results in release of hydrocarbons, potential injury to personnel. | 1 | 1 | 22.1 | Hoses to be certified for hydrocarbon liquid service when using OBM. Pressure test hoses prior to starting operations. Use a hose certified for gas service in high risk operations (natural gas injection, etc.). Use hard line whenever possible. |  | Rig Contractor | Rig Equipment
4. Drilling | 112 | ALL | Well has to be killed for well control | Y | Formation damage. Ignition and explosion risks. Potential harm to personnel. | 1 | 1 | 22.4.3 22.4.5 | Kill fluid must be available on site, as per regulatory requirements. Operations Matrix in place, and observed. Well control procedure in place and rehearsed. |  | Operating Company | Well Control
4. Drilling | 113 | ALL | Poor understanding of the relationship of the UBD/MPD/RMD kit and the rig kit with regards to well control events | Y | Failure in well control procedure may result in well control problems, loss of control, injury or death. | 1 | 1 | 22.7 | On-site orientation and training is to include well control considerations. Discuss at pre-job safety meeting. Clear plans for well control operations utilizing rig chokes Understanding and checks of valve alignment for well control operations Consider labeling valves and marking them as normally open or normally closed Process flow diagram in doghouse including description of well control or shutdown events |  | Operating Company / UBD/MPD/RMD Service Provider | Well Control
4. Drilling | 114 | UBD/MPD | BHA NRV failure | Y | Possible gas/reservoir fluid communication to surface. May require well kill to trip safely. Unable to trip with remedying the situation (well kill, set a plug, or retrieve/replace NRV). | 1 | 1 | 22.12 22.16.3 | Test NRVs before initial installation. Replace BHA NRVs after every trip. Include contingency to set a plug or another retrievable NRV as deep as possible. Install screens above NRV to catch debris from the drill string. Run a minimum of two NRVs in the BHA. |  | Operating Company | NRV
4. Drilling | 115 | ALL | PWD Failure/MWD Annular Pressure fails | Y | Operational parameters often consider availability of real time PWD data. Absence of PWD data may result in poor decision making regarding well control. Possible trip out of the hole (cost). Uncertainty regarding down hole pressure. | 2 | 1 |  | Review requirements for PWD data and importance with directional company prior to starting operations. Include decision points in program regarding PWD data failure. Maintain a well calibrated two phase flow model throughout operation. Use pressure data obtained from MPD software. Implement pumping program in accordance with MWD tool SOPs to minimize potential for tool failure. UBD program should include potential decision points to trip, including whether the operation can safely proceed without PWD data. |  | MWD Contractor / UBD/MPD/RMD Service Provider | MWD
4. Drilling | 116 | ALL | Inaccurate flow simulation | Y | Potential to operate outside of Operations Matrix due to wrong input data. | 2 | 2 |  | Review fluid data and simulation software use with RMD/MPD/UBD service provider. |  | UBD/MPD/RMD Service Provider | Well Control
4. Drilling | 117 | UBD/MPD | Rig crew unaware of dangers of trapped pressure below NRV | Y | Possible damage to equipment, injury, or loss of life if NRV is broken out with trapped pressure below it. | 1 | 1 | 22.12 22.7.3 | Improper use of NRVs are a leading cause of HSE incidents in UBD/MPD operations. Review supplier's SOPs and implement their use in accordance with the RP referenced. |  | Operating Company / UBD/MPD/RMD Service Provider | NRV
4. Drilling | 118 | GAS INJECTION OPS (UBD/MPD) | No written procedures in place for bleeding off the NRV | Y | Possible damage to equipment, injury, or loss of life if NRV is broken out with trapped pressure below it. | 1 | 1 | 22.12 | Improper use of NRVs are a leading cause of HSE incidents in UBD/MPD operations. Review supplier's SOPs and implement their use in accordance with the RP referenced. |  | Operating Company / UBD/MPD/RMD Service Provider | NRV
4. Drilling | 119 | GAS INJECTION OPS (UBD/MPD) | Inadequate pressure rating for NRV bleed-off hose and tool | Y | Possible injury or loss of life if hose or tool fails. | 1 | 1 | 22.12 | Improper use of NRVs are a leading cause of HSE incidents in UBD/MPD operations. Review supplier's SOPs and implement their use in accordance with the RP referenced. |  | Operating Company / NRV Provider | NRV
4. Drilling | 120 | GAS INJECTION OPS (UBD/MPD) | NRV bleed-off hose in poor condition | Y | Possible injury or loss of life if hose fails. | 1 | 1 | 22.12 | Improper use of NRVs are a leading cause of HSE incidents in UBD/MPD operations. Review supplier's SOPs and implement their use in accordance with the RP referenced. |  | Operating Company | NRV
4. Drilling | 121 | GAS INJECTION OPS (UBD/MPD) | NRV bleed-off hose is not securely anchored | Y | Hose may whip and injure/kill personnel on the rig floor. | 1 | 1 | 22.12 | Improper use of NRVs are a leading cause of HSE incidents in UBD/MPD operations. Review supplier's SOPs and implement their use in accordance with the RP referenced. |  | Operating Company | NRV
4. Drilling | 122 | UBD/MPD | Retrievable NRV unseats under pressure | Y | Unseated NRV can cause serious damage to equipment or injury/death. | 1 | 1 | 22.12 | Improper use of NRVs are a leading cause of HSE incidents in UBD/MPD operations. Review supplier's SOPs and implement their use in accordance with the RP referenced. Do not allow unqualified personnel to seat, inspect, or touch retrievable NRVs. |  | NRV Supplier | NRV
4. Drilling | 123 | MPD/RMD | Well is accidentally shut in while pumping single phase (liquid) | Y | Possible formation breakdown at weak point. Well control problems/blowout. | 1 | 1 | 22.4.6 | Job planning must include maximum allowable surface pressure for the mud weight used for the operation. Operational adjustments must be made based on the formation integrity test/leak off gradient. Consider installing a pressure relief valve upstream of the choke. |  | UBD/MPD/RMD Service Provider | Choke/Flowline
4. Drilling | 124 | ALL | Air introduced into circulating system while making drill pipe connection/tripping | Y | Potential for explosive mixtures and/or fire (surface or downhole). | 1 | 1 | 22.4.8 Energy Safety Canada Fire and Explosion Hazard Management Guideline | Job planning stage is to consider the air volume required to create a combustible/reactive mixture downhole based on the drilling fluids being used, reservoir fluids, etc. |  | Operating Company | Well Program
1. Planning | 125 | UBD/MPD | Insufficient pressure measurement points | Y | Overpressure of equipment, error in well control operations may result in equipment damage or injury to personnel. | 1 | 1 | 22.4.3 22.10 | P&ID to include electronic and manual pressure measurement points. Confirm requirements at pre-spud and rig visit. |  | UBD/MPD/RMD Service Provider | Data Acquisition
4. Drilling | 126 | UBD/MPD | Need to flow through equalizing line | Y | Unclear well control strategy, responsibility for operating valves/chokes may result in well control problems. | 1 | 1 | 22.4.3 22.11 | Consult Process Flow Diagrams for appropriate recommendations. |  | UBD/MPD/RMD Service Provider | Well Control
4. Drilling | 128 | UBD/MPD | Insufficient kill fluid / kill fluid density on location | Y | Loss of well control. | 1 | 1 | 22.4.5.3 | Reference appropriate regulatory body regarding minimum kill fluid volume requirements. Kill fluid must be readily accessible. |  | Operating Company | Well Control
4. Drilling | 129 | ALL | Flow through tubing spool or casing bowl | Y | Washout below BOP may result in loss of well control. | 1 | 1 | 22.1 | No flow allowed through any 2" (or smaller) flow. No flow through equalization lines. Not designed for flow from drilling operations. May contravene regulations depending on juristiction. |  | Operating Company / UBD/MPD/RMD Service Provider | Well Control
4. Drilling | 130 | UBD/MPD | Dual annular BOP is used for surface pressure containment | Y | Potential hydrocarbon release, pressure at the rig floor, etc. if the stripping annular fails. | 1 | 1 | 22.4.3 | Safety consideration are similar to the use of RCDs. Ensure that the design of the stack meets recommended practices. |  | RCD Supplier | RCD
4. Drilling | 131 | MPD/RMD | Excessive back pressure during single-phase (liquid) MPD operations | Y | Possible formation breakdown at weak point. Well control problems/blowout. | 1 | 1 | 22.4.6 | Job planning must include maximum allowable surface pressure for the mud weight used for the operation. Operational adjustments must be made based on the formation integrity test / leak off gradient. Consider installing a pressure relief valve upstream of the choke. |  | UBD/MPD/RMD Service Provider | Choke/Flowline
4. Drilling | 133 | ALL | Inaccurate or insufficient PVT measurements | Y | Failure to detect kicks/losses (and intensity) may result in well control incident. | 1 | 1 | 22.4.3 | P&ID to include electronic and manual pressure measurement points. Confirm requirements at pre-spud and rig visit. Use of mass flow meters. |  | UBD/MPD/RMD Service Provider | Data Acquisition
4. Drilling | 134 | ALL | Changing flash point of oil based drilling fluid | Y | Flashpoint and fluid properties change with inflow. | 1 | 1 | 22.16.3 | Use closed fluid storage system when drilling UB with oil based system. Monitor fluid properties while drilling. |  | Rig Contractor | Mud System
1. Planning | 135 | UBD/MPD | Inability to transfer fluid from storage tanks to active system | Y | Unable to access fluid for well control purposes. | 1 | 1 | 22.4.5 | Confirm requirements at pre-spud and rig visit. Confirm regulatory requirements for type of operations UBD/MPD |  | Operating Company | Well Control
4. Drilling | 137 | UBD/MPD | High-rate flush production encountered | Y | High inflow rates could exceed separator ratings (liquids or gas). Increased potential for pipe erosion. Possibly suspend operations before planned TD. Exceed RCD pressure rating. | 1 | 2 | 22.4.2 | Size separator for flush production events. Accurately measure return flow parameters - rates and pressures. Develop and post Operations Matrix in dog house and UBD/MPD control room. |  | UBD/MPD/RMD Service Provider | Separation
4. Drilling | 138 | UBD/MPD | ESD closes on the primary flow line from the BOP stack to the separation equipment | Y | Over pressure RCD, resulting in failure and/or gas release at rig floor. Exceed formation strength at shoe. | 1 | 2 | 22.11.2 | The use and benefits of and ESD need to be weighed against the potential hazards of operating the ESD (intentionally or accidentally). UBD/MPD program should justify the use (or lack thereof) of an ESD. |  | UBD/MPD/RMD Service Provider | Well Program
1. Planning | 139 | ALL | Unplanned condensate/oil production | Y | Possible adverse effects on fluid system. Possible surface separation challenges or storage problems. Flammability/explosion risk in Air Drilling operations. | 1 | 2 | 22.16.3 | Monitor fluid trends for signs of oil/condensate production. Program to include contingency plans if oil/condensate production is a possibility, including dealing with emulsions. |  | Operating Company / UBD/MPD/RMD Service Provider | Well Program
4. Drilling | 142 | UBD/MPD | Failure to bleed off float down to atmospheric pressure | Y | Any trapped pressure below the NRV poses a risk to personnel. | 1 | 2 | 22.11.4 | Improper use of NRVs are a leading cause of HSE incidents in UBD/MPD operations. Review supplier's SOPs and implement their use in accordance with the RP referenced. |  | Operating Company / NRV Provider | NRV
4. Drilling | 143 | UBD/MPD | Bleed-off to atmosphere is located in an area where workers are present | Y | Workers are exposed to flying debris, hazardous mist. | 1 | 2 | 22.11.4 | Improper use of NRVs are a leading cause of HSE incidents in UBD/MPD operations. Review supplier's SOPs and implement their use in accordance with the RP referenced. |  | UBD/MPD/RMD Service Provider | NRV
4. Drilling | 146 | ALL | Flare pilot goes out | Y | Odours. Potential explosive mixture. Optics for crew of potential explosion risk. | 2 | 2 |  | Continuous pilot ignition system. Methane disperses rapidly into atmosphere. High concentration of nitrogen may reduce flare ignition and combustion efficiency. |  | UBD/MPD/RMD Service Provider | Flare/Vent System
4. Drilling | 147 | ALL | Geological sampling system not working or plugged | Y | Non-conformance with regulatory requirement to collect samples. Potential harm to personnel, clearing plugged sample catcher. | 2 | 2 |  | Consider dual sample catcher manifold system. Must be able to isolate sample catcher from primary flow line. Service company to provide/follow sample catching procedure. Adjust sample catching procedure based on volume of samples caught each time. |  | UBD/MPD/RMD Service Provider | Sample Catcher
4. Drilling | 148 | GAS INJECTION OPS (UBD/MPD) | Chemical injection pumps are not working or not calibrated | Y | Risks of carryover from separator (environmental concern). Corrosion concerns. | 2 | 2 |  | Test injection pumps during rig up and commissioning. Store chemicals as per manufacturers recommendations. Consider connecting injection pumps to data system. Spare pumps/parts are to be available onsite. |  | UBD/MPD/RMD Service Provider | Mud System
4. Drilling | 149 | UBD/MPD | High surface back pressure | Y | Overpressure or exceed flow control/operational matrix. Harm to personnel or environment. Damage to equipment. Possible loss of well control. | 1 | 1 | 22.7.5 | Switch to second choke on dual-choke manifold. Include choke plugging in the planned/unplanned shutdown operations. Consideration for auto type chokes Follow SOPs. Follow drilling program. Switch to secondary choke. Have adequate mud density on location. Have contingency SOPs. Operations matrix to be posted so it is visible to choke operator and in the doghouse. |  | UBD/MPD/RMD Service Provider | Choke/Flowline
4. Drilling | 150 | UBD | Higher than planned gas/oil inflow rates | Y | Flowline erosion. Noise (flaring). Higher potential for equipment failure. | 2 | 2 |  | Follow Operations Matrix in program. Ensure separator PSV capacity is appropriate for anticipated maximum possible gas flow rate. |  | Operating Company | Well Program
4. Drilling | 153 | GAS INJECTION OPS (UBD/MPD) | Near Surface NRV failure | Y | NRV leaking while making a connection. Slight injection gas/fluid blow from drill pipe at surface. Lost time to trip and replace leaking NRV. | 2 | 2 |  | Test NRVs before initial installation. Install screens above NRV to catch debris from the drill string. Run wireline retrievable NRVs. If the surface gas is a flammable substance and the hose or any part of the injection system faile then a contingency plan needs to be in place to deal with the flammable release. |  | Operating Company | NRV
4. Drilling | 155 | GAS INJECTION OPS (UBD/MPD) | Chemicals are used in injection/return system | Y | Health hazards of workers exposed to chemicals. | 2 | 3 |  | Appropriate protective gear to be available based on MSDS/SDS sheets of all chemicals on location. |  | Mud Company | Mud System
4. Drilling | 160 | UBD/MPD | Problem or situation which causes sudden pressure increase downhole. | Y | Overbalanced pressure spike Possible formation damage. | 3 | 1 |  | Follow UBD/MPD program procedures. Monitor trends on data system for signs of increasing BHP, decreasing inflow rates, etc. |  | Operating Company | Well Program
4. Drilling | 161 | GAS INJECTION OPS (UBD/MPD) | Gas injection system fails | Y | Possible overbalanced situation (formation damage). Lost time and cost. | 3 | 1 |  | Procedure in place for unplanned and planned shutdown of gas injection system. Consider back-up compression requirements. Compression equipment supplier to provide maintenance schedule / onsite parts list. Gas injection metering may require frequent calibration checks and consideration for redundant meters. Providing backup to the natural gas drilling euqipment. If the surface gas is a flammable substance and the hose or any part of the injection system faile then a contingency plan needs to be in place to deal with the flammable release. |  | Compression Supplier | Compression
4. Drilling | 162 | GAS INJECTION OPS (UBD/MPD) | Mist pump failure | Y | Lost time and cost. Higher BHP than planned. Unstable BHP. Stuck pipe/poor hole cleaning. MWD failure. | 3 | 1 |  | Procedure in place for unplanned and planned shutdown of gas injection system. Function test prior to starting operations. Install screens in the suction line and ensure clean fluid is being pumped. |  | UBD/MPD/RMD Service Provider | Well Program
4. Drilling | 165 | GAS INJECTION OPS (UBD/MPD) | Unstable flow in annulus | Y | Compromised hole cleaning could increase potential for stuck pipe. Difficult to interpret inflow rates and well behavior. | 3 | 2 |  | Conduct frequent mud or foam checks. Change pump rates/surface back pressure to change flow regime in wellbore. |  | UBD/MPD/RMD Service Provider | Well Program
4. Drilling | 166 | ALL | Hole cleaning problems | Y | Formation damage. Stuck pipe. Lost BHA/fishing costs. Target not reached. | 3 | 2 |  | Follow MPD/UBD program for hole cleaning procedures and monitoring. Understand hole cleaning capabilities and environment if multiphased system. Monitor returns. |  | Operating Company / UBD/MPD/RMD Service Provider | Well Program
4. Drilling | 167 | GAS INJECTION OPS (UBD/MPD) | Unplanned formation water production | Y | Formation damage to reservoir section already drilled. Possibly suspension of air drilling program. Fluid handling/storage/trucking issues. | 3 | 2 |  | Monitor fluid trends for signs of water production and make trajectory adjustments accordingly. UBD/MPD program to consider contingency with regards to pump rates required for hole cleaning (air--foam-two-phase transitions). Consider a contingency plan to deal with emulsions. |  | Operating Company | Well Program
4. Drilling | 168 | UBD | Low inflow rates | Y | Increased hole cleaning concerns. Possible equipment damage due to increased drill string/well purge time required. | 3 | 2 |  | Observe MWD supplier's recommendation for maximum allowable nitrogen injection rate. Increase awareness of possible hole cleaning problems. |  | Operating Company | Well Program
4. Drilling | 169 | UBD/MPD | Excessive drill string connection time | Y | Lost time and cost. Unstable BHP. Possible formation damage from pressure spikes. | 3 | 2 |  | Connection procedures in place and rehearsed. Back pressure schedule available and updated by UBD/MPD Engineer to optimize connection procedure to minimize BHP spikes. |  | Rig Contractor / UBD/MPD Service Provider | Training
4. Drilling | 170 | ALL | Surveying problems | Y | Lost time and cost. Unstable BHP. Possible formation damage from pressure spikes. | 3 | 2 |  | Connection procedure discussed with MWD personnel before being finalized. Connection procedure must consider MWD tool requirements and limitations. Consideration for EMMWD tools for when injecting two-phase fluids into drill string. Positive pulse MWD has limitations with two-phase fluids above 20-30% gas volume fraction in the standpipe. |  | MWD Contractor | MWD
5. Tripping | 172 | UBD/MPD | Pipe light | Y | Drill string ejected from well. Damage to equipment and/or injury/death of personnel. Pipe buckling. | 1 | 1 | 22.2 | Pipe light calculations to be updated based on current well parameters. Pipe light calculations need to be done before tripping out of the hole. |  | Operating Company | Well Program
5. Tripping | 173 | UBD | High flow rate from well | Y | Increased RCD wear, pipework erosion. | 1 | 1 | 22.4.2 22.4.6 22.10.4 | Determine decision points for when various equipment is required, including push-pull equipment, and rig assisted snubbing units. |  | Operating Company | Well Program
5. Tripping | 174 | UBD/MPD | RCD failure - stripping through RCD | Y | Immediate release of gas/wellbore fluids to the rig floor. Risk of ignition, injury or death. | 1 | 1 | 22.4.6 22.11.3 22.15.3 | Operate RCD within supplier's specifications. Inspect RCD element before tripping. Consider replacing RCD element when bit is back at the shoe and/or pre-emptively at bit trips. Flow well to reduce the flowing well head pressure. |  | RCD Supplier | RCD
5. Tripping | 175 | UBD/MPD | Equalizing procedure not implemented for changing RCD elements | Y | Immediate release of gas/wellbore fluids to the rig floor. Risk of ignition, injury or death. | 1 | 1 | 22.11.3 | Operate RCD within supplier's specifications. Follow procedure recommended by RCD supplier when equalizing pressure. Review BOP diagram during prespud. Vent bleed off to a safe area. |  | RCD Supplier | RCD
5. Tripping | 176 | UBD/MPD | RCD failure - with snubbing adaptor | Y | Immediate release of gas/wellbore fluids to the rig floor. Risk of ignition, injury or death. | 1 | 1 | 22.2 | Operate/install snubbing adaptor as per supplier's specifications. Inspect/pressure test integrity of snubbing adaptor pressure seal on RCD before commencing snubbing operations. |  | RCD Supplier | RCD
5. Tripping | 177 | ALL | RCD seal integrity is unknown | Y | Release of gas/wellbore fluids to the rig floor. Risk of ignition, injury or death. | 1 | 1 | 22.12 22.16.1 | Wear device should "leak" rather than fail catastrophically. |  | RCD Supplier | RCD
5. Tripping | 178 | UBD/MPD | BHA NRV failure | Y | Possible gas/reservoir fluid communication to surface. May require well kill to trip safely. Unable to trip with remedying the situation (well kill, set a plug or retrieve/replace NRV). | 1 | 1 | 22.3.21 22.7.6 22.12 22.15 22.19 | Test NRVs before initial installation. Replace BHA NRVs after every trip. Include contingency to set a plug or another retrievable NRV as deep as possible. Install screens above NRV to catch debris from the drill string. Run a minimum of two NRVs in the BHA. |  | Operating Company / NRV Provider | NRV
5. Tripping | 179 | GAS INJECTION OPS (UBD/MPD) | NRV Bleed-off tool fails | Y | Release of injection gas at rig floor. Possible injury/death to personnel if bleed-off tool fails mechanically or hose comes lose. | 1 | 1 | 22.3.21 22.7.6 22.11.4 22.13 22.15.4 | Improper use of NRVs are a leading cause of HSE incidents in UBD/MPD operations. Review supplier's SOPs and implement their use in accordance with the RP referenced. |  | NRV Supplier | NRV
5. Tripping | 180 | ALL | Reservoir pressure is higher than anticipated | Y | Deeper pipe light point. Increased RCD wear/failure potential. | 1 | 1 | 22.4.2 22.4.6 | Pipe light calculations and associated equipment requirements to be updated based on current well parameters. |  | Operating Company | Well Control
5. Tripping | 181 | UBD/MPD | Snubbing unit failure | Y | Lost time and cost. | 1 | 1 | 22.2 | Snubbing unit to be equipped with fail safe slip design to prevent pipe light condition. Pre-job inspection minimizes the potential for equipment downtime. Unsupported pipe length buckling calculations shall be made. |  | Snubbing Contractor | Well Program
5. Tripping | 182 | ALL | Annular BOP failure | Y | Potential gas release to surface. Potential loss of well control equipment. | 1 | 1 | 22.1 | Consider the use of variable pipe rams as backup to the annular. Cannot change RCD element until Annular BOP (and a second barrier) are both operational. |  | Rig Contractor | Well Control
5. Tripping | 183 | UBD/MPD | Washout in primary flowline (while Stripping) | Y | Higher surface pressure if well has to be shut in. | 1 | 2 | 22.12 22.15.4 22.21 | Procedure in place (and rehearsed) to divert to equalization line or secondary flowline (if present) to fix leak. |  | UBD/MPD/RMD Service Provider | Choke/Flowline
5. Tripping | 185 | UBD/MPD | Varying outer diameters in BHA | Y | Increased cross sectional area increases snubbing force and associated risks. | 1 | 2 | 22.12 22.16.1 | Use maximum diameter for pipe light calculations. Operate pipe heavy and pipe light slips. Avoid running jars and bumper subs. If stripping through RCD ensure all BHA components are strippable. |  | Snubbing Contractor | Well Program
5. Tripping | 187 | UBD | Low gas flow rate from reservoir (<0.25 MMscfd) | Y | Low pressure at surface reduces perceived risk to personnel and the environment. Actual risk may not be different. | 2 | 2 |  | Well is to be considered live despite low inflow rate. RCD to remain engaged at all times - well is never to be open to atmosphere. Monitor wellhead flowing pressure for changes throughout operation. |  | Operating Company | Well Program
5. Tripping | 188 | UBD | Flowing temperature changes | Y | Possibility for hydrates. Potential equipment damage, injury/death to personnel if hydrate breaks loose. | 2 | 2 |  | Methanol and injection pump available on site. Calculations should be done in the well planning stage to define the temperature/pressure window under which hydrates may develop. |  | UBD/MPD/RMD Service Provider | Choke/Flowline
1. Planning | 189 | UBD/MPD | Inadequate space to rig up snubbing equipment | Y | Formation damage if the well has to be killed for trips. Possible injuries to personnel if trying to rig up equipment in extremely tight space. | 2 | 2 |  | UBD program is to include the snubbing procedures and equipment to be used. Snubbing contractor should be involved in pre-spud. |  | Snubbing Contractor | Well Program
5. Tripping | 190 | UBD/MPD | Failure in communications during stripping/snubbing operations | Y | Possible damage to equipment. Injury to personnel. Gas/well bore fluids release to surface. | 2 | 2 |  | Procedures to be reviewed in a safety meeting prior to commencing stripping/snubbing operations. |  | Operating Company | Lease Management
5. Tripping | 191 | UBD/MPD | Driller has poor visibility of work floor due to snubbing unit or push pull unit | Y | Potential damage to equipment. Hazard to personnel. | 2 | 2 |  | Rig up in best location possible. Conduct JSA and hazard assessment prior to commencing operations. |  | Snubbing Contractor | Well Program
5. Tripping | 192 | UBD/MPD | Complex BHAs, tubular dimensions and inability to stage tools | Y | Gas release at rig floor. | 2 | 2 |  | BHA tools/drawings are required in the planning stages. Only strippable components, or components that can be staged in the hole easily should be installed. | . | Snubbing Contractor | Well Program
5. Tripping | 193 | GAS INJECTION OPS (UBD/MPD) | Near Surface NRV failure | Y | Uncertainty with regards to whether near surface, or BHA NRVs are leaking may take some time. | 3 | 3 |  | Bleed off string, inflow test and continue tripping if BHA NRV integrity exists. Only BHA NRVs are a major concern when tripping. |  | Operating Company | NRV
6. Wireline | 194 | UBD/MPD | RCD adaptor fails | Y | Immediate release of gas/wellbore fluids to the rig floor. Risk of ignition, injury or death. | 1 | 1 | 22.5.5 22.10.5 2.15.4 22.16.2 | Operate/install snubbing adaptor as per supplier's specifications. Inspect/pressure test integrity of snubbing adaptor pressure seal on RCD before commencing snubbing operations. |  | RCD Supplier | RCD
6. Wireline | 195 | UBD/MPD | Wireline lubricator leaks/fails. | Y | Gas/wellbore fluids release at surface. Potential harm to personnel. | 2 | 2 |  | Low probability of occurrence. Pressure test with water or nitrogen before equalizing. |  | Wireline Contractor | Wireline Tools
6. Wireline | 196 | UBD/MPD | Grease injector head fails | Y | Gas release at surface. | 2 | 2 |  | Run wireline BOPs. |  | Wireline Contractor | Wireline Tools
6. Wireline | 198 | UBD/MPD | No pressure gauge on lubricator | Y | Potential damage to equipment, harm to personnel. | 2 | 2 |  | Manual gauge must be installed on the lubricator. |  | Wireline Contractor | Wireline Tools
6. Wireline | 199 | UBD/MPD | Unable to run in hole due to pressure | Y | Delays (time and cost). Gas leaks through pack-off. | 2 | 3 |  | Standard cased-hole/open-hole equipment is not set up for operating at high surface pressures. Run grease injector. |  | Wireline Contractor | Well Program
1. Planning | 200 | UBD/MPD | Improper RCD wireline adapter on location | Y | Wait on equipment (time and cost). | 3 | 1 |  | Confirm requirements for adaptor in pre-spud or when calling out the wireline unit. |  | RCD Supplier | RCD
7. Suspend Well for Rig Out or Completion | 202 | UBD/MPD | Pipe light condition occurs while running tubing | Y | Damage to equipment. Injury to personnel. | 1 | 1 | 22.15.4 22.16.2 | Same controls as stripping/snubbing drill pipe out of the hole are required. |  | Operating Company | Well Program
7. Suspend Well for Rig Out or Completion | 203 | UBD/MPD | Plug in tubing or tubing end plug fails | Y | Immediate gas flow to surface. | 1 | 1 | 22.15.4 22.16.2 | Stabbing valve with crossover to tubing connection must be made up and ready for use on the rig floor. Consider having profile sub with nipple as part of tubular string. |  | Operating Company | Well Program
7. Suspend Well for Rig Out or Completion | 204 | UBD/MPD | Potential for bridge plug to leak after pressure testing | Y | Pressure at surface while rigging out BOP can have catastrophic HSE results. | 1 | 2 | 22.16.2 | A double barrier is required when rigging out the BOP stack. |  | Operating Company | Well Program
7. Suspend Well for Rig Out or Completion | 205 | UBD/MPD | Dognut leaks when BOPs are being rigged out | Y | Gas flow at surface without well control. Possible loss of well, injury/death to personnel. | 1 | 2 |  | Maintain the ability to flow the well to the separation package until the well head is secured. Check for leaks continuously while unbolting BOPs. Keep nuts on well head studs while first raising BOPs. |  | Operating Company | Well Program
7. Suspend Well for Rig Out or Completion | 206 | UBD/MPD | Tubing or wireline set bridge plug fails to pressure test | Y | Unable to nipple up well head. | 2 | 2 |  | Retrieve plug and set a new plug. |  | Operating Company | Well Program
7. Suspend Well for Rig Out or Completion | 207 | UBD/MPD | Pressure testing a plug with pipe in the hole | Y | High surface pressure could cause a pipe light condition. Potential damage to equipment, injury to personnel. | 2 | 2 |  | Pipe light calculations must be made prior to pressure testing if pipe is in the hole while testing. |  | Operating Company | Well Program
7. Suspend Well for Rig Out or Completion | 209 | UBD/MPD | Unable to land dognut/tubing in wellhead | Y | Time and cost. Potentially have to kill the well. | 2 | 2 |  | Run wear bushing while drilling to minimize potential of damaging the wellhead. Note that the wear bushing may also create a problem in that it may be difficult to remove. Written procedure recommended for landing the dognut. |  | Operating Company | Well Program
8. Rig Out | 219 | ALL | Improperly purged equipment | Y | Potential explosive gas release while rigging out. Vessel entry for clean up is not possible with explosive gas in vessel. | 2 | 3 |  | Purge lines with inert gas or water prior to rigging out. Check LEL prior to using hammer on hammer unions - use brass hammer. Use separator that can be cleaned without entering. Ensure flare is distinguished. |  | UBD/MPD/RMD Service Provider | Separation
1. Planning | 220 | ALL | Aspiration of O2 from ambient air into the drill pipe or well | Y | Explosive mixtures. Fire and explosion. Damage to downhole equipment and/or well casing. | 1 | 1 | Energy Safety Canada Fire and Explosion Hazard Management Guideline 22.7.7 | Ensure well is never placed on vacuum. Always fill drill string with liquid or inert gas during tripping. Always maintain monitorable positive pressure on wellbore. |  | UBD/MPD/RMD Service Provider | Well Control
5. Tripping | 221 | UBD/MPD | Lubricator spacing for staging in/out odd sized drill/work string components | Y | Not able to remove drill string components. Increase drill string integrity risk with connections below lowermost NRV. Bit must be pulled closer to the diverter element prior to closing the blind ram during tripping. Cannot install packers and/or completion assemblies in well. | 2 | 2 |  | Adding spacer spool between RCD and annular preventer. Adding a pony sub under the rig. Sumping casing bowl. Using smaller BOP diameter. Using double gate rams. Connection of lowermost BOP to tubing head spool (no DSA). |  | Rig Contractor | Well Control
5. Tripping | 222 | UBD/MPD | Loss of drill string integrity below the lowermost NRV | Y | Loss of well control. Fire/explosion. | 1 | 1 | 22.12 | Inflow test all connections below the lowermost NRV prior to removal from the well using annular preventer and RCD. Conduct motor pump test prior to pulling motor through RCD. Maximize lubricator space to minimize the number of connections below the lowermost NRV that have to be removed from the well prior to closing the blind ram. Consider adding an NRV below the motor and/or as close to the bit as possible. |  | Rig Contractor | Well Control
1. Planning | 223 | ALL | UBD/MPD/RMD Equipment Rental | Y | Improper equipment size. Inadequate required surface back pressure. Potential gas inflow. Potential equipment failure. Potential well control issues. Additional methane injection equipment on location (UBD). | 1 | 1 |  | Conduct review with reservoir/production engineers regarding potential inflow rates. Review separator sizing requirements with service company. Review offset information for the area. (RMD) Clear understanding of RMD operating limits and parameters. (RMD) RMD checklist (MPD) Clear understanding of personnel responsibilities. (MPD) MPD Checklist (UBD) Clearly define methane responsibilities |  | UBD/MPD/RMD Equipment Provider | MPD/UBD/RMD Equipment Rental
4. Drilling | 225 | ALL | Degasser fails/overflows | Y | Harm to environment. Fluid carryover may cause a fire, environmental damage/injury. | 2 | 2 |  | Ensure degasser fluid level/capacity. Operate within well program specifications. Operate within equipment specifications. |  | UBD/MPD/RMD Service Provider | Separation
4. Drilling | 226 | ALL | Use of secondary flowline (rig bleed-off line) | Y | Loss of well control. Harm to equipment and personnel | 1 | 1 |  | Operate within well scope. Ensure adequate drilling fluid weight and surface back pressure (SBP). Ensure adequate kill mud on location. |  | UBD/MPD/RMD Service Provider | Well Program
4. Drilling | 227 | ALL | Inadequate/improper RCD size | Y | Harm to personnel or environment. Damage to equipment. Possible loss of well control. | 1 | 1 |  | Review offset data for area. Follow drilling program. Plan for maximum pressures expected. Ensure contingency plans are in place. |  | All | RCD
2. Rig Up / Pressure Test / Commissioning | 228 | UBD | Fueling equipment | Y | Harm to personnel and equipment. | 2 | 2 |  | Ensuring adequate fuel gauge and grounding. Review SOPs. |  | Rig Contractor / UBD Service Provider | All
1. Planning | 229 | ALL | Flashback from flare | Y | Fire Explosion Loss of containment Harm to personnel and equipment Potential well control issues. | 1 | 1 | 22.7.7 | Flame arrestor (preferred) or other regulator approved backflash prevention mechanism in flare line. Include in P&ID and PFD's. Winter conditions and maintainance. Include a bypass or PRV. Ensure proper inspection and maintenance. |  | UBD/MPD/RMD Service Provider | MPD/UBD/RMD Equipment Rental
1. Planning | 230 | RMD | Poor understanding of formation's capability to flow. | Y | High risk of taking influx. RMD Technique assumes a 'tight' formation. May be significantly underbalanced to formation resulting in significant influx. | 1 | 1 | Appendix I | Proper assessment, history of drilling and understanding of formation and natural fracturing. Zone should be assessed as not capable of flow without stimulation. Experience and history in vicinity. Design for kick tolerance and or mud weights planned. |  | Operating Company | Well Control
4. Drilling | 231 | RMD | Lack of understanding of RMD operation. | Y | Miss indications of kick warning signs. A large kick/influx may be taken. Operating outside of operating matrix. | 1 | 1 |  | Proper understanding of the RMD operation. RMD checklist prior to rig up of equipment. Predrill out meetings and drills. |  | Operating Company | Well Control
4. Drilling | 232 | RMD | Lack of understanding of RMD equipment. | Y | Improper use of equipment. Run equipment beyond capabilities. Harm to personnel, spills, loss of containment, well control. | 1 | 1 |  | RMD checklist Proper program and zone assessment by operating company Predrillout discussions and drills |  | Operating Company | MPD/UBD/RMD Equipment Rental
1. Planning | 233 | ALL | Tying rig choke system to MPD/UBD/RMD degasser | Y | Confusion or uncertainty of flow path during well control operations. Plugging of flowline or degasser with shale from drilling ahead. Assuming adequate flow capacity for all situations including well control events. Harm to personnel and equipment Potential well control issues. | 1 | 1 |  | Clear plans for well control operations utilizing rig chokes. Understanding of valve alignment for well control operations. Process flow diagram including description of well control or shutdown events. Plugging risk increased in higher ROP / larger hole applications Use of secondary inlets into MPD separator Understand degasser capacity in planning and performance while drilling Potential for H2S in area |  | Operating Company / UBD/MPD/RMD Service Provider | Well Control
4. Drilling | 234 | ALL | Plugging of flowline or degasser with shale from drilling ahead when tying rig choke system to MPD/UBD/RMD degasser. | Y | Plugging risks increased in higher ROP / larger hole applications. | 1 | 1 |  | Use of secondary inlets into MPD separator. Understand degasser capacity in planning and performance while drilling. |  | Operating Company / UBD/MPD/RMD Service Provider | Well Control
4. Drilling | 235 | ALL | Erosion of flowline or degasser when tying rig choke system to MPD/UBD/RMD degasser. | Y | Erosion of flowline or degasser while drilling through in MPD/UBD/RMD operation. | 1 | 1 |  | Circulate through system prior to initiating well control through MPD degasser. (If feasible) Implement pipe inspection procedures and documentation prior to each rig up, and NDT wall thickness inspections at vulnerable points throughout operation. UT testing when possible. Refer to API Standards. Use of secondary inlets into MPD separator. |  | Operating Company / UBD/MPD/RMD Service Provider | Well Control
4. Drilling | 236 | ALL | Uncertainty or confusion of flow path during well control operations | Y | Failure in well control procedure may result in well control problems, loss of control, injury or death. Confusion when tying rig choke system to MPD/UBD/RMD degasser. | 1 | 1 |  | Clear plans for well control operations utilizing rig chokes. Understanding and checks of valve alignment for well control operations. Consider labeling valves and marking them as normally open or normally closed. Process flow diagram in doghouse including description of well control or shutdown events. |  | Operating Company / UBD/MPD/RMD Service Provider | Well Control
4. Drilling | 237 | ALL | Tying rig choke system to MPD/UBD/RMD degasser. | Y | Understanding that the rig degasser as primary degasser in a well control event. | 1 | 1 |  | Rig degasser sizing appropriate for application. Ability to switch back to rig degasser needs to be maintained. Use of MPD degasser as a secondary option. Regulations (AER Directive 36) require rig degasser be present as a primary degasser. |  | Operating Company | Well Control
1. Planning | 238 | ALL | Improper degasser sizing when tying rig choke system to MPD/UBD/RMD degasser. | Y | Over running rig degasser or MPD/UBD/RMD degasser. Plugging of MPD/UBD/RMD degasser due to cuttings volumes causing issues in well control event. | 1 | 1 |  | Ensure understanding and documentation of rig degasser capacity. Understand and have documentation on MPD/UBD/RMD degasser capacity. Have means to measure gas volumes through MPD/UBD/RMD degasser. |  | UBD/MPD/RMD Service Provider | Well Control
4. Drilling | 239 | ALL | Shut down due to problems in MPD surface equipment when tying rig choke system to MPD/UBD/RMD degasser | Y | If need to switch from MPD operations to rig well control due to shutdown from wash in MPD/UBD/RMD equipment. | 1 | 1 |  | Understand reaction plan if MPD/UBD equipment failure downstream of chokes. Use of secondary inlets into MPD separator. Utilize rig degasser as primary in case of emergency shut down. Ensure all well control piping blown dry and/or heated to prevent freezing. |  | UBD/MPD/RMD Service Provider | Well Control
1. Planning | 240 | ALL | Encounter H2S in well control event when tying rig choke system to MPD/UBD/RMD degasser | Y | Damage/Failure of MPD/UBD/RMD equipment due to H2S | 1 | 1 |  | If potentially sour fluids are encountered ensure MPD separation equipment and flowlines H2S certified. If utilizing MPD/UBD/RMD separation equipment in a well control event understanding potential for H2S. |  | UBD/MPD/RMD Service Provider | Well Control
4. Drilling | 241 | UBD/MPD | UBD/MPD choke washout | Y | Temporary loss of backpressure control. Harm to personnel or environment. Damage to equipment. Possible loss of well control. | 1 | 1 |  | Switch to second choke on dual-choke manifold. Include choke washout in the planned/unplanned shutdown operations. Follow SOPs. Follow drilling program. Switch to secondary choke. Have adequate mud density on location. Have contingency SOPs. |  | UBD/MPD/RMD Service Provider | Choke/Flowline
9. Other Hazards and Operations | 242 | UBD/MPD | Cementing using Managed Pressure Techniques in a casing string with a hanger landed in the wellhead | Y | If hydrostatically underbalanced, there is only one barrier which may lead to loss of containment during a well control event | 1 | 1 |  | Wellhead design requires fluted mandril or the returns will have to be taken below the master ram (i.e., include an additional spool to act as the master ram). |  | UBD/MPD/RMD Service Provider | Choke/Flowline
2. Rig Up / Pressure Test / Commissioning | 243 | UBD | Pressure testing surface lines | Y | Potential injury/explosion hazard if a surface line with natural gas in it fails to pressure test. | 1 | 2 |  | Require the ability to pressure test all natural gas surface lines from source to standpipe. Require the ability to drain the lines after pressure tests. Use an intert gas to pressure test if injecting natural gas or methane. |  | Separation Services Provider | Compression
R
Y
G
R
Y
G

## Hazard Register GENERAL
Operational Phase | Item | Relevance (UBD/MPD/RMD/All) | Hazard Scenario What If ? | Applicable | Threats/Consequences | HSE | NPT | Required HSE Critical Controls / Safeguards | Considerations | Actions to be taken / By Who and When | Primary Responsible Party | Primary Category
1. Planning | 1 | ALL | Improper kelly (square vs. hex) | Y | RCD leakage. Injury to personnel. Unable to run square kelly through RCD. Delay in drilling well (lost time and cost). | 1 | 1 | 22.11.3 22.14.2 | Use hex kelly, square kelly not recommended. Use power swivel instead of kelly. Use top drive instead of kelly. Use coiled tubing. RCD supplier standard operating procedures/risk register. Drill string diagram. |  | Rig Contractor | Rig Equipment
1. Planning | 2 | ALL | Lease size inadequate | Y | Poor emergency response. Problems fitting equipment on location. Decreased access/egress in case of emergency. Inadequate flare spacing on location. Tree clearance could cause forest fire. Delay in rig up and start up of operations | 1 | 1 | 22.7.4 Appendix G | Verify lease survey accuracy and working area available. Verify rig specific layout accuracy. Confirm working area on lease once constructed. Primary UBD/MPD/RMD service supplier to provide site specific lease spacing diagram. Primary UBD/MPD/RMD service provider to conduct site inspection as soon as possible. Use drill side pipe racks only (if possible). Verify regulatory stack height/flaring requirements. |  | UBD/MPD/RMD Service Provider | Separation
1. Planning | 3 | ALL | Concurrent rig up of rig and UBD/MPD/RMD package causes confusion | Y | Harm to personnel. Lost time and cost. | 1 | 1 | 22.2.1 22.15.2 | Onsite supervisors to formulate rig up plan. Company man to coordinate overall strategy. Safety hand to be involved during rig up. |  | Operating Company / UBD/MPD/RMD Service Provider | Lease Requirements
1. Planning | 4 | ALL | Improper rig alignment | Y | Potentially wash/wear casing bowl, and cause RCD failure or BOP failure. Potential loss of well control if bowl wears out. Casing wear | 1 | 1 | 22.11.3 22.14.3 | Check rig alignment before nippling up BOP/RCD. Check rig alignment during UBD/MPD/RMD operation. |  | Rig Contractor | RCD
1. Planning | 11 | ALL | Insufficient tank farm berms | Y | Release of drilling fluid to environment. | 1 | 1 | 22.4.5 22.4.5.5 Appendix D Appendix G | Applicable provincial regulations to be followed. |  | Operating Company | Separation
1. Planning | 16 | ALL | Coiled Tubing - Coil pack-off fails | Y | Gas/Fluid at rig floor (potential hydrocarbon release, ignition or fire). Harm to personnel. Formation damage if well must be killed. | 1 | 1 | 22.26.2 IRP21 | Begin operation with new stripper elements. Inspect sealing elements after each trip. Back up elements available on location. Monitor for leakage during operation. |  | RCD Supplier / Coiled Tubing Contractor | Training
1. Planning | 17 | ALL | Coiled Tubing - Coil string failure (downhole washout) | Y | Potential loss of well. Formation damage if well has to be killed. Increased risk to personnel while tripping. | 1 | 1 | 22.26.2 IRP 21 | Carefully define coil operating limits. Monitor coil fatigue life. Pressure test coil before job. Use appropriate corrosion inhibitor package. Minimize high pressure coil cycling. | . | Coil Tubing Contractor | Well Program
1. Planning | 18 | ALL | Coiled Tubing - Coil string failure (surface washout) | Y | Gas/fluid release at rig floor (potential hydrocarbon release/ignition/fire). Harm to personnel. Formation damage if well must be killed. Environmental damage. | 1 | 1 | 22.26.2 IRP 21 | Carefully define coil operating limits. Monitor coil fatigue life. Pressure test coil before job. Use appropriate corrosion inhibitor package. Minimize high pressure coil cycling. Run leak point back into well if possible. |  | Coil Tubing Contractor | Well Program
1. Planning | 20 | ALL | Temporary pipe and hammer union mismatch | Y | With several and diverse companies on site the potential for mismatched hammer union connections are greatly increased. Threat of personnel injury and environmental spills. | 1 | 1 | 22.12.1 | Ensure clear policy and direction is provided on acceptable temporary pipe design and hammer unions. Ban hammer unions with potential for mismatch. |  | UBD/MPD/RMD Service Provider | Choke/Flowline
1. Planning | 25 | ALL | Inadequate fire protection for additional equipment | Y | Injury, loss of equipment. | 1 | 2 |  | Add fire containment equipment. |  | Operating Company | Lease Requirements
1. Planning | 26 | UBD/MPD | Oxygen deficient environments | Y | Potential for injury. | 1 | 2 | 22.16 | Identify potentially oxygen deficient areas and include in onsite orientation. Workers in high risk areas must wear appropriate monitoring device. |  | All | N/A
1. Planning | 27 | ALL | Response to alarm condition is not clearly defined | Y | Confusion on location increases HSE risks. | 1 | 2 | 22.16 | Clearly define response to alarm conditions and communicate the response to personnel on location. |  | Operating Company | Lease Requirements
1. Planning | 28 | ALL | Multiple alarm systems on location | Y | Confusion on location increases HSE risks. | 1 | 2 | 22.16 | Clearly define response to alarm conditions and communicate the response to personnel on location. Additional monitoring required for UBD/MPD equipment. |  | Operating Company | Lease Requirements
1. Planning | 34 | ALL | Muster area is not clearly defined. | Y | Increased risk for personnel to search location for missing workers. | 1 | 3 | 22.16 | Clearly define muster area during wellsite safety meetings. |  | Operating Company | Lease Requirements
1. Planning | 37 | ALL | Condition of drill pipe and kelly (grooves, external scale, etc.) | Y | RCD leakage. Injury to personnel. Premature RCD element wear. Delay in drilling well (lost time and cost). | 2 | 1 |  | Use dill pipe without grooves. Use pipe with no hard banding. Use drill pipe with flush hard banding. Service kelly to eliminate sharp edges and ensuring kelly is as straight as possible. RCD supplier pre-job inspection. Drill pipe/kelly inspection. RCD supplier SOPs/risk register. Drill string diagram. Kelly savers with rubber inserts are not recommended as they can severely damage the RCD element. Avoid abrupt OD transitions between Kelly and drill pipe. |  | Rig Contractor | Drill String
1. Planning | 39 | ALL | Working on pad wells | Y | Simultaneous operations on pad wells increases risk of HSE incidents. | 2 | 1 |  | Determine whether other operations will occur on pad at the same time as the drilling operation. Ensure that one site supervisor is appointed and that lines of authority are clear. |  | Operating Company | Lease Requirements
1. Planning | 42 | ALL | Rental equipment in poor repair | Y | Equipment failure during critical times may elevate existing HSE risks. | 2 | 1 |  | Inspect all rental equipment upon arrival on location. RMD checklist |  | Operating Company | All
1. Planning | 45 | ALL | Inadequate lease spacing for flare. | Y | Risk of forest fire. | 2 | 2 |  | Consult appropriate forestry regulations. Ensure required fire mitigation is in place (sprinkler system, water storage, etc.) |  | Operating Company | Separation
1. Planning | 46 | ALL | Inadequate lighting. | Y | Increased potential for HSE incidents such as slips, trips or falls. | 2 | 2 |  | Conduct review of lighting requirements with service companies at pre-spud. Consider constructing a lighting diagram. Rent light towers as required. |  | Operating Company | Lease Requirements
1. Planning | 47 | ALL | Equipment not flushed/cleaned pre/post job | Y | Contamination of fluids on location with prior job waste. | 2 | 2 |  | Inspect equipment upon arrival and before being released. |  | Operating Company | Separation
1. Planning | 48 | ALL | Unclear responsibility for rental equipment | Y | Potential equipment failure if not used properly. | 2 | 2 |  | Determine responsibility during pre-spud and confirm in onsite safety meetings. |  | Operating Company | All
1. Planning | 49 | ALL | Exposure to wildlife | Y | Risk to personnel or wildlife. | 2 | 2 |  | Communicate risks of bears, etc. during safety meeting. Establish protocol for personnel leaving location on foot. |  | Operating Company | Lease Requirements
1. Planning | 50 | ALL | Equipment/Personnel Congestion | Y | Noise, pressure, vibration, egress, communication - Miscommunication=Potential for injury/death. | 2 | 2 |  | Formal Chain of command. Formal lockout/tag out/control of work. Formal PTW/Logistics Plan. Review IRP 7 Standards for Wellsite Supervision of Drilling, Completions and Workovers. |  | All | Lease Management
1. Planning | 55 | ALL | Coiled Tubing - Slips fail to hold BHA components | Y | Tools dropped in hole, resulting in lost time, high-risk fishing operation. Potential gas/fluid release at rig floor. | 2 | 2 | IRP21 | Manage risk with appropriate procedures and checks to make sure slips are engaged and holding. Consult IRP21 Coiled Tubing Operations |  | Coil Tubing Contractor | Well Program
1. Planning | 56 | UBD/MPD | Drill string NRV’s missing or wrong size/thread | Y | No drill string well control. Delay in drilling well (lost time and cost). Drill string damage. | 2 | 3 |  | Wait on correct NRVs/subs. NRV supplier standard operating procedures/risk register. Drill string diagram. |  | NRV Supplier | NRV
1. Planning | 57 | ALL | Flare gun ignites forest or grassland | Y | Risk to environment/personnel. | 2 | 3 |  | Consider using an auto-ignition system if flaring in an area or time of year when there is a high risk of fire. |  | UBD/MPD Service Provider | Separation
1. Planning | 59 | ALL | Equipment available/Timing | Y | Delay in drilling well (lost time and cost) | 3 | 1 |  | Ensure adequate communications between supplier and operator. Confirm timing at pre-spud. |  | Operating Company | N/A
1. Planning | 62 | UBD/MPD | Improperly specified PDMs | Y | Frequent motor failures or poor performance increases number of trips required along with the associated risks. Wait on PDM’s suitable for UBD/MPD environment – temperature and fluid compatibility. | 3 | 2 |  | Ensure PDM supplier is aware of downhole operating environment for application. Inspect data for PDMs received vs. order placed. |  | Directional Company | PDM
1. Planning | 63 | UBD/MPD | Dump subs in motors are not blanked off | Y | Wait on blanked dump subs and/or trip out of hole. | 3 | 2 |  | Motor supplier should be involved in planning stage to ensure that the proper motor specification is being supplied. |  | Directional Company | PDM
1. Planning | 64 | ALL | Solids - Vac truck handling | Y | Release of toxic gas near separator | 3 | 2 |  | Formal Communication method - radios |  | Operating Company | Lease Management
1. Planning | 65 | ALL | Solids - re-injection down drill string | Y | Plugged BHA Drill string washouts. | 3 | 2 |  | Suction side discipline Suction Screens |  | UBD/MPD/RMD Service Provider | Separation
1. Planning | 66 | ALL | Re-entry - Casing exit debris in well | Y | Higher and/or unstable BHP. Tight hole or stuck pipe. Plugged choke/separator dump valves. Damage to bit and/or BHA. | 3 | 2 |  | Consider magnet/junk basket run to clean out casing exit. Monitor torque/drag carefully throughout drilling and tripping through exit. |  | Operating Company | Well Program
1. Planning | 67 | ALL | Solids - waste management | Y | Environmentally responsible disposal of H2S contaminated cuttings | 3 | 3 |  | AER Directive 50: Drilling Waste Management (see www.aer.ca) Operating Company waste management policies |  | Operating Company | Lease Management
2. Rig Up / Pressure Test / Commissioning | 69 | UBD/MPD | Loss of radio communication | Y | Harm to personnel due to erroneous communications. Lost time and cost. | 1 | 1 | 22.15.3 | Ensure hand signals are in place for important communications. Establish radio protocol in safety meeting. Supply sufficient head sets for men working in high-noise environments. Understand limits of equipment Establish battery changing schedule. |  | Operating Company / UBD/MPD/RMD Service Provider | Lease Management
2. Rig Up / Pressure Test / Commissioning | 70 | ALL | Lifting hazards | Y | Harm to personnel and/ or damage to equipment. Lost time and cost. | 1 | 1 | 22.15.14 | Company man to coordinate hoisting activities with picker operator and supervisors. Pre-fab BOP components can be difficult to install in low clearance areas. Safety hand to be involved during rig up. Spotting UPD/MPD equipment. |  | Picker Operator / UBD/MPD/RMD Service Provider | Lease Management
2. Rig Up / Pressure Test / Commissioning | 71 | ALL | Inadequate or non-existent work platforms/barriers (i.e. RCD work platform) | Y | Trip and fall hazards particularly around RCD installation/removal and seal element change out. | 1 | 1 |  | Install suitable work decks and barriers for any elevated work tasks, particularly RCD installations. Adequate communication |  | Operating Company / UBD/MPD/RMD Service Provider | RCD
2. Rig Up / Pressure Test / Commissioning | 72 | ALL | Ambient temperatures below freezing | Y | Possible freezing in piping dead legs, liquid traps, etc. with resultant blockage. | 1 | 1 |  | Consider heat tracing and/or warm air/N2 circulation to maintain clear lines. Avoid liquid traps in installation, utilize "clear line" start up procedure. |  | Operating Company / UBD/MPD/RMD Service Provider | Lease Management
2. Rig Up / Pressure Test / Commissioning | 73 | ALL | Inadequate or non-existent electrical grounding of equipment skids | Y | Improperly or non-grounded equipment skids leading to personnel injury and equipment downtime. | 1 | 1 |  | Implement an electrical grounding plan for the installation. Inspect and test installation for electrical grounding. Ensure proper grounding during transport. |  | All | All
2. Rig Up / Pressure Test / Commissioning | 74 | ALL | Inadequate or non-existent electrical lockout/tag out procedures. | Y | Personnel injury, equipment damage when prematurely powering up electrical circuits. | 1 | 1 |  | Implement electrical lockout/tag out procedures. |  | All | All
2. Rig Up / Pressure Test / Commissioning | 75 | ALL | Inadequate or non-existent lockout/tag out procedures for utility supply (i.e. instrument air) | Y | Personnel injury, equipment failure, environmental spills as a consequence of inadvertent removal of skidded equipment utility supply (i.e. instrument air). | 1 | 1 |  | Implement lockout/tag out procedures for temporary skidded equipment utility supply. |  | All | All
2. Rig Up / Pressure Test / Commissioning | 76 | ALL | No high-pressure warning signs on pipework | Y | Increased risk to personnel. | 1 | 2 |  | Review in safety meetings. Inspect prior to pressure testing. Inspect temporary pipe work. |  | UBD/MPD/RMD Service Provider | Separation
2. Rig Up / Pressure Test / Commissioning | 77 | ALL | RCD fails to pressure test | Y | Lost time and cost. | 2 | 1 |  | Ensure adequate spares on location. Visually check rig annular (ring gaskets/stud threads) prior to rig up. Ensure proper rig alignment. |  | RCD Supplier | RCD
2. Rig Up / Pressure Test / Commissioning | 78 | ALL | BOP elements fail to pressure test | Y | Lost time and cost. | 2 | 1 |  | BOP should be tested and serviced as per AER Directives prior to job. Rig should stock spare components as appropriate. |  | Rig Contractor | BOP System
2. Rig Up / Pressure Test / Commissioning | 79 | ALL | Primary flow line from stack to separation equipment fails to pressure test | Y | Lost time and cost. | 2 | 1 |  | Service company must be able to demonstrate MTR, certification for pipework. Supplier to provide SOP for rig up and pressure test. Rig matting to be supplied in muddy/soft ground conditions to enable proper makeup/alignment of pipework. |  | UBD/MPD/RMD Service Provider | Choke/Flowline
2. Rig Up / Pressure Test / Commissioning | 80 | ALL | Crew shortage and/or inexperience | Y | Harm to personnel. Lost time and cost. | 2 | 1 |  | Onsite orientation and training. Supervisors to ensure that all personnel have been trained in the various components of the rig up operation. Identify tasks in tool box safety meetings. Ensure all workers understand their right to refuse unsafe work, or request training/guidance for tasks that they are not yet competent in. Consider EMS onsite during rig up operations. Identify inexperienced crew/short term crew with green hand or green hard hats. |  | All | Lease Management
2. Rig Up / Pressure Test / Commissioning | 84 | ALL | Weather conditions | Y | Harm to personnel. Lost time and cost. | 2 | 2 |  | Supervisors have obligation to stop unsafe work/activities. Additional rig-up time. Element storage. Winterizing equipment. |  | Operating Company | Lease Management
2. Rig Up / Pressure Test / Commissioning | 85 | ALL | Poor ground conditions | Y | Ice, mud, uneven terrain can increase potential for slips, trips and falls. | 2 | 2 |  | Consider extensive use of rig matting. Sawdust, etc. to be available to improve footing on snow/ice in winter operations. |  | Operating Company | Lease Management
2. Rig Up / Pressure Test / Commissioning | 86 | UBD/MPD | Compression or N2 unit fails to start | Y | Lost time and cost. | 3 | 1 |  | Commission in yard test if unit has been idle for a significant length of time. Service company to show maintenance records. Inspect fuel tanks before filling with diesel onsite. |  | Compression Supplier | Compression
2. Rig Up / Pressure Test / Commissioning | 88 | ALL | Poor quality diesel fuel on location | Y | Equipment damage, and lost time. Pump/compressor failure during UBD/MPD operations may result in well control issues. | 3 | 1 |  | Adequate fuel filtering system to be in place for all critical components. Inspect rental fuel storage tanks before filling (especially 400 bbl tanks not normally used for fuel storage). |  | Operating Company / UBD/MPD/RMD Service Provider | Compression
3. Drill Out and Hole Conditioning | 97 | ALL | Float shoe debris in well after drillout | Y | Higher BHP than predicted. Unstable BHP. Stuck pipe. Plugged choke. Damage to BHA/bit. | 3 | 2 |  | Drill out while pumping at high rate. Consider tooth bit versus PDC. Monitor torque and drag while drilling shoe. Observe returns at shaker. Direct returns to shaker, bypassing separator. Control drill through plug. Consider drilling out with slick assembly. |  | Operating Company | Drill String
3. Drill Out and Hole Conditioning | 98 | ALL | Damage to BHA during drillout | Y | Potential harm to personnel if BHA floats fail. Lost time and cost due to round trip. Compromised BHA integrity may result in a well control scenario. | 3 | 2 |  | Displace to gasified/drilling fluid system in controlled manner after drillout. Ensure all injection rate meters are functioning and the required rate is being pumped. Observe pressures during hole conditioning. |  | Directional Company | MWD
4. Drilling | 109 | ALL | Drill string failure (washout or twist-off) | Y | Possible gas/hydrocarbon fluid at rig floor. Ignition and explosion risk. Formation damage due to well kill. Possible pipe light situation. | 1 | 1 | 22.4.4.3 22.16.2 | Establish maximum torque limit on pipe during drilling operations. Inspect all drill string components according to the appropriate risk assessed API or DS-1 category. Monitor drilling data for signs of pipe washout. Include drill string failure in planned/unplanned shut-down procedures. |  | Rig Contractor | Well Program
4. Drilling | 110 | ALL | Kelly hose failure | Y | Gas/fluid release at rig floor. Harm to personnel. Ignition and explosion risks. Formation damage if well has to be killed. | 1 | 1 | 22.14.4 22.16.2 | Consider installing new kelly hose prior to commencing UBD operations. Kelly hose to be certified for hydrocarbon liquid service when using OBM. Run surface drill pipe screens periodically and check for rubber debris. Pressure test kelly hose prior to starting operations. Consider using a hose certified for gas service in high risk operations (natural gas injection, etc.). Kelly hose issues also apply to other flexible rubber components in the rig's mud circulation system. |  | Rig Contractor | Rig Equipment
4. Drilling | 127 | ALL | Improperly configured BOP stack | Y | Well control problems may not be dealt with safely, resulting in possible loss of well control. | 1 | 1 | 22.4.3 22.10 | Consult Process Flow Diagrams for appropriate recommendations. |  | Operating Company | Well Control
4. Drilling | 132 | ALL | Blind ram or pipe ram failure. | Y | Potential loss of well control. | 1 | 1 | 22.1 | Flush BOP stack prior to using components for operational purposes. Check regulator pressure for rams and annular to ensure maximum closing pressures are observed. Minimize cycling of BOPs. |  | All | Well Control
4. Drilling | 136 | ALL | Wellhead cellar full of liquid/mud, immersion hazard | Y | Possible immersion hazard in the event of a trip or fall. | 1 | 2 | 22.15.1 | Pump out and barrier off cellar prior to RCD, etc. rig up. |  | Operating Company | Lease Management
4. Drilling | 140 | ALL | Unclear responsibilities of key personnel on location. | Y | Delay in implementing well control procedures may increase the potential for a severe well control incident. | 1 | 2 | 22.15.3 | A diagram containing key personnel roles, responsibilities, and reporting structure improves communications and data dissemination on location. |  | Operating Company / UBD/MPD/RMD Service Provider | Lease Management
4. Drilling | 141 | ALL | Unclear reporting lines/structure on location | Y | Delay in implementing key decisions may result in well control incidents, exceeding equipment ratings, etc. | 1 | 2 | 22.15.3 | A diagram containing key personnel roles, responsibilities, and reporting structure improves communications and data dissemination on location. |  | Operating Company / UBD/MPD/RMD Service Provider | Lease Management
4. Drilling | 144 | ALL | Top drive seal and/or wash pipe failure | Y | Release of gas/fluids at rig floor. Ignition/explosion risk. Potential harm to personnel. | 1 | 3 | 22.16.3 | Service and inspect before job. |  | Rig Contractor | Rig Equipment
4. Drilling | 145 | ALL | MWD tool failure | Y | Trip out of the hole. | 2 | 1 |  | Implement pumping program in accordance with MWD tool SOPs to minimize potential for tool failure. Choose tools with a high MTBF in the demanding UBD environment. |  | MWD Contractor | MWD
4. Drilling | 151 | ALL | Damage to wellhead sealing areas | Y | Can't set tubing hanger. Tubing hanger won't seal. Wellhead leaks. | 2 | 2 |  | Consider installing wear bushing during UBD operation. Make sure rig alignment is good throughout operation. Isolate well with packer/bridge plug, then run hanger/pressure test and check sealing areas. |  | Operating Company | Well Program
4. Drilling | 154 | ALL | Failure to continuously monitor data stream accuracy | Y | Possibly designing well procedures based on wrong information. | 2 | 2 |  | Data technician or other responsible person to maintain data system and assure data integrity. All decision makers on location should have access to the real time data stream. |  | UBD/MPD/RMD Service Provider | Data Acquisition
4. Drilling | 156 | ALL | Excessive casing wear | Y | Loss of well. | 2 | 3 |  |  |  | Operating Company | Well Program
4. Drilling | 157 | ALL | Leaks in low pressure tank farm pipework | Y | Environmental spill, potential fire hazard. | 2 | 3 |  | Establish procedure to monitor for leaks. Procedures must be in place for shipping fluid, ensuring that no pipework is over-pressured. |  | RCD Supplier | Separation
4. Drilling | 158 | ALL | Spill during offloading/loading drilling fluid | Y | Environmental spill, potential fire hazard. | 2 | 3 |  | Review trucking contractor's SOPs. Inspect condition of trucking contractors shipping lines. All employees must go through the onsite orientation. |  | Trucking Contractor | Mud System
4. Drilling | 159 | ALL | Drill out of zone into shale or coal | Y | Planned hole depth not achieved. Costs incurred with sidetracking. Possible stuck pipe, loss of BHA. | 3 | 1 |  | Ensure bottoms up calculation times for sample retrieval is accurate. Monitor changes in ROP/inflow/changes in directional control, and other drilling parameters to flag lithology changes. Monitor changing LWD data, if available. |  | Directional Company | Well Program
4. Drilling | 163 | ALL | Borehole instability | Y | Formation damage. Stuck pipe. Lost BHA/fishing costs. Target not reached. | 3 | 1 |  | Manage drawdown throughout all stages of the operations. Include minimum pressure to prevent breakout as a well design parameter. Avoid exiting into shale/coal seams, and avoid planning a trajectory that crosses known trouble zones. Minimize time in the hole without circulating. |  | Operating Company / UBD/MPD/RMD Service Provider | Well Program
4. Drilling | 164 | ALL | Torque and drag are too high | Y | Planned hole depth is not achieved. Drill string failure. Pipe buckling. Stuck pipe. | 3 | 2 |  | Check drill string specifications and recent inspections. Implement good drilling practices - minimize doglegs, monitor hole cleaning parameters, conduct wiper trips when required. Include chemical options for friction reducers in the planning stage of the well. |  | Operating Company | Well Program
5. Tripping | 171 | ALL | Drill string integrity failure | Y | Gas release at rig floor. Potential pipe light. | 1 | 1 | 22.4.4.3 | Test integrity prior to drillout. Test drill string integrity when breaking out last near-surface NRV. |  | Operating Company | Well Control
5. Tripping | 184 | ALL | Buckling, yield, or collapse of drill string | Y | Damage to equipment. Injury to personnel. | 1 | 2 | 22.4.4.3 | Calculate buckling strength. Confirm calculations with maximum operating WHP. |  | Snubbing Contractor | Well Program
5. Tripping | 186 | ALL | Failure to properly torque pipe connections while tripping | Y | Pipe connection may come apart. Potential loss of BHA/wellbore. | 2 | 1 |  | Very unlikely scenario. Follow SOPs for making up and breaking out connections while tripping. |  | Snubbing Contractor | Well Program
6. Wireline | 197 | UBD/MPD | Logging tools get stuck in the hole | Y | Lost time and cost. | 2 | 2 |  | Fishing operation may require the well to be killed. Loss of weight of tools may cause the wireline to be expelled out of the hole (even with a grease injector rigged up). Consider LWD as an alternative. |  | Wireline Contractor | Fishing
7. Suspend Well for Rig Out or Completion | 208 | UBD/MPD | Tight hole or stuck pipe when running tubing | Y | Time and cost. Potentially have to kill the well. | 2 | 2 |  | Ensure good hole cleaning on last trip out of the hole with drill pipe/bit. Conduct scraper run prior to running production packers. |  | Operating Company | Well Program
7. Suspend Well for Rig Out or Completion | 210 | UBD/MPD | Liquid remains in the hole prior to well suspension/completion | Y | Formation damage may result (cost). | 3 | 3 |  | Conduct adequate blow-down of well (dry gas scenario) in liquid sensitive formations. |  | Operating Company | Well Program
8. Rig Out | 211 | UBD/MPD | Wellhead fails or is damaged during rig out | Y | Potential hydrocarbon release at surface. Harm to personnel. | 1 | 1 | 22.16.2 | Well suspension plan to be in place and approved by operator. Rig out plan to be reviewed on site. |  | Operating Company | Well Program
8. Rig Out | 212 | ALL | Lifting hazards | Y | Harm to personnel. Lost time and cost. | 1 | 1 | 22.2.1 22.15.14 | Company man to coordinate hoisting activities with picker operator, and supervisors. Pre-fab BOP components can be difficult to install in low clearance areas. Safety hand to be involved during rig up. |  | Picker Operator | Lease Management
8. Rig Out | 213 | UBD/MPD | Loss of radio communication | Y | Harm to personnel due to erroneous communications. Lost time and cost. | 1 | 1 | 22.15 | Ensure hand signals are in place for important communications. Establish radio protocol in safety meeting. Supply sufficient head sets for men working in high-noise environments. Establish battery changing schedule. |  | Operating Company | Lease Management
8. Rig Out | 214 | ALL | Concurrent rig out of rig and UBD/MPD/RMD package causes confusion | Y | Harm to personnel. Lost time and cost. | 1 | 1 | 22.15.1 | Onsite supervisors to formulate rig up/out plan. Company man to coordinate overall strategy. Safety hand to be involved during rig up. |  | Operating Company | Training
8. Rig Out | 215 | UBD/MPD | Crew shortage and/or inexperience | Y | Harm to personnel. Lost time and cost. | 2 | 1 |  | Onsite orientation and training. Supervisors to ensure that all personnel have been trained in the various components of the rig up operation. Identify tasks in tool box safety meetings. Ensure all workers understand their right to refuse unsafe work, or request training/guidance for tasks that they are not yet competent in. Consider EMS onsite during rig up operations. |  | All | Training
8. Rig Out | 216 | ALL | Inadequate lighting | Y | Increased potential for HSE incidents such as slips, trips or falls. | 2 | 2 |  | Conduct review of lighting requirements with service companies at pre-spud. Consider constructing a lighting diagram. Rent light towers as required. |  | Operating Company | Lease Management
8. Rig Out | 217 | ALL | Poor ground conditions | Y | Ice, mud, uneven terrain can increase potential for slips, trips and falls. | 2 | 2 |  | Consider extensive use of rig matting. Sawdust, etc. to be available to improve footing on snow/ice in winter operations. |  | Operating Company | Lease Management
8. Rig Out | 218 | ALL | Poor weather | Y | Harm to personnel. Lost time and cost. | 2 | 2 |  | Supervisors have obligation to stop unsafe work/activities. |  | Operating Company | Lease Management
3. Drill Out and Hole Conditioning | 224 | UBD/MPD | In Casing Test | Y | Damage to equipment. | 3 | 3 |  | Bit to casing clearance. Follow detailed SOPs. Ensure homogeneous mud in hole. |  | UBD/MPD/RMD Service Provider | Well Program
R
Y
G
R
Y
G

## Operational Phases
1. Planning
2. Rig Up / Pressure Test / Commissioning
3. Drill Out and Hole Conditioning
4. Drilling
5. Tripping
6. Wireline
7. Suspend Well for Rig Out or Completion
8. Rig Out
9. Other Hazards and Operations

## Relevance
AIR DRILLING
GAS INJECTION OPS (UBD/MPD)
UBD
MPD
UBD/MPD
RMD
ALL
UBD/RMD
MPD/RMD

## Primary Responsible Party
3rd Party Rental
All
Coil Tubing Contractor
Compression Supplier
Directional Company
Mud Company
MWD Contractor
MWD Contractor / UBD/MPD/RMD Service Provider
NRV Supplier
Operating Company
Operating Company / NRV Provider
Operating Company / UBD/MPD/RMD Service Provider
Picker Operator
Picker Operator / UBD/MPD/RMD Service Provider
RCD Supplier
RCD Supplier / UBD/MPD/RMD Service Provider
RCD Supplier / Coiled Tubing Contractor
Rig Contractor
Rig Contractor / UBD/MPD/RMD Service Provider
Rig Contractor / UBD/MPD Service Provider
RMD Equipment Provider
RMD Service Provider
Safety Services
Separation Services Provider
Snubbing Contractor
Trucking Contractor
UBD/MPD/RMD Equipment Provider
UBD/MPD/RMD Service Provider
Wireline Contractor

## Primary Category
All
BOP System
Choke/Flowline
Compression
Data Acquisition
Drill String
Fishing
Flare/Vent System
Lease Requirements
Lease Management
Mud System
MWD
MPD/UBD/RMD Equipment Rental
N/A
NRV
PDM
RCD
Rig Equipment
Sample Catcher
Separation
Training
Well Control
Well Program
Wireline
Wireline Tools

## YesNo
Y
N