## Introduction (hidden)
IRP 24 Hazard Register
Column Headings
Column Letter
Item | A | Sequential item number for hazards in each operational phase.
Hazard Scenario What If | B | Single jeopardy statement used to identify potential problems due to failure in pre-job planning, training, procedures, or equipment failure.
Applicable | C | Choose "Y" if "Hazard Scenario What If" applies to operation and "N" if it does not.
Threats/Consequences | D | A list of the potential consequences (HSE and NPT) of the "what if" occurring.
HSE | E | The risk of a situation/event with the potential to cause harm (to people, assets, or the environment).
NPT | F | The risk of Non Productive Time (NPT), including lost time and costs, formation damage and/or any deviation from the plan.
Required HSE Critical Controls / Safeguards | G | Controls/safeguards, and detailed recommended practices for high risk HSE items and referenced to specific prescriptive IRP 24 enforced requirements.
Considerations | H | Recommendations, considerations, and informational statements on how to reduce, eliminate, or manage Medium/Low Risk HSE items and all NPT items.
Actions to be Taken / By Who and When | I | List of actions required to reduce/eliminate the potential occurrence and/or severity if the hazard cannot be eliminated entirely. Who = Party/parties responsible for each action assigned. When = Date by which the action is to be completed.
Operational Phase | J | Categorization of the hazard scenario by operational phase.
Primary Responsible Party | K | Categorization of the hazard scenario by primary responsible party.
Primary Category | L | Categorization of the hazard scenario by primary category (equipment, well program, etc.)
Risk Ranking - severity of the event (consequence multiplied by likelihood of occurrence)
1 |  | High Risk - Engineering, Procedures, and Training required to control/mitigate risk.
2 |  | Medium Risk - Procedures and Training required to control/mitigate risk. Should consider Engineering.
3 |  | Low Risk - Training required to control/mitigate risk. Should consider Engineering and Procedures.
General Notes about Register

## Subject Well Integrity
Item | Sub IRP | Category | Position | Hazard Scenario What is existing? | Applicable | Cause How can this happen? | Threats / Consequences What events/incidents can result? | HSE | NPT | Required HSE Critical Controls / Safeguards | Industry Suggested Controls and Mitigations How can this be prevented? | Actions to be taken / By Who and When | Frequency of Exposure | Probability of Loss | Consequences | Risk Ranking | Operational Phase | Primary Responsible Party | Related to Item
1 |  |  |  | Incorrect barrier envelope AMP |  | - Inadequate assessment of the condition of a barrier element - Missing a barrier element in the assessment - inadequate assessment of the condition of the well, downhole environment (such as exposure to H2S), and/or the potential forces and loading conditions - erosion, corrosion, mechanical wear - plastic formations (e.g., salt formations) - high pressure / low permeability formations | - Loss of barrier envelope integrity in the SW | 1 | 1 |  | `- Re-assess Subject Well history and how it affects the condition of barrier elements - Conduct pressure integrity tests to better assess the condition of a barrier element - Run logs to better assess the condition of a barrier element - Review the flowpath to capture all barrier elements - Review force analysis to ensure inclusion of all loading conditions such as temperature induced stresses from the fracture fluids - Review downhole environmental exposure conditions to determine appropriate reductions in barrier element integrity - Conduct a proper assessment of minimum external pressures to determine net burst pressures. - Consider hydrostatic column of treating slurry - Review the fracture stimulation program treatment rates and pressures to assure a appropriate/conservative estimate of maximum treament pressure. | [7 empty] | 24.2.2.1 Subject Well Barrier Analysis
2 |  |  |  | Maximum treatment pressure / barrier envelope AMP is exceeded |  | - Very rapid increase in fracture treatment pressure due to near wellbore issues (e.g., sand-off, failure of frac-port to open) | - Loss of barrier envelope integrity in the SW | 1 | 1 |  | - Lower shut-off pressure for fracture pumps - Analyze historical fracture-treatment charts for pressure trends to better understand the likelihood of a rapid increase in fracture treatment pressure - Provide an ESD bleed-off system for immediate pressure relief - consider an adequate allowance for a combination of fluid hammer, surge and pressure caused by reaction shut-down time.
3 |  |  |  | Fracturing close to the base of groundwater |  | - target zone is shallow, therefore potentially close to groundwater | - communication to groundwater | 1 | 1 |  | - Evaluate the barrier envelope protecting groundwater - Ensure the barrier envelope(s) around the zone of groundwater account for integrity issues unique to shallow fracture operations - Adhere to Directive 083: Hydraulic Fracturing; non-saline aquifer protection and Hydraulic fracturing near water wells sections. - Utilize groundwater-friendly fracture systems (e.g., fluids and additives) | [7 empty] | 24.1.4 Shallow Well Fracture Stimulation
4 |  |  |  | New casing burst or collapse below manufacturers' specification |  | - casing has defects (manufacture, metallurgy, yield strength, cracks) - casing integrity compromised by transportation damage, handling and installation procedures (e.g., over-torqued connections, under-torqued connections) | casing failure | 1 | 1 |  | `- review transportation, handling and installation procedures - audit manufactuerer QA/QC - review mill order MTRs - adjust purchasing specification guidelines
5 |  |  |  | Maximum treatment pressure is higher than secondary barrier envelope AMP |  | - secondary barrier envelope not designed to withstand fracture treatment pressures | - secondary barrier envelope could fail if exposed to the planned treatment | 1 | 1 |  | - monitor the secondary barrier envelope - implement a shut-down and bleed-off plan - determine the practicality of upgrading secondary barrier envelope.
6 |  |  |  | Trapped pressure behind casing |  | fracture pressure trapped in a void behind casing | casing collapse when internal pressure is reduced | 1 | 1 |  | - select casing with collapse ratings comparable to burst ratings
7 |  |  |  | inadequate hydraulic isolation near the heel of a well in a dual barrier system |  | inadequate cement quality resulting from a lack of sufficient cement volume past the heel section of the well | communication may occur to overlying porous intervals that are relatively close to top of production zone - casing collapse - loss of treatable zone(s) near heel of well | 1 | 1 |  | - install a liner and pump excess cement
8 |  |  |  | well becomes sour during production |  | interaction of fracture fluid and formation chemicals - fracture into an adjacent sour zone | sour gas reduced integrity of casing | 1 | 1 |  | - consider the potential of the well becoming sour - ensure adequte use of biocide in the fracture fluid - use sour resistance tubulars for wells that may become sour - review geology - review production history
9 |  |  |  | Internal diameter changes in the fracture treatment flowpath |  | wellbore configuration and construction creates conditions potentially resulting in turbulence or increased wear from a single flow stream impinging directly on the adjacent wall of the frac adapter. | - internal erosion causing barrier envelope failure | 1 | 1 |  | `- change components in the wellbore - lower the fracture treatment pump rate -when tying in frac lines try to match opposing pairs on the same frac adapter (aka goat head or buffalo head)
10 |  |  |  | long pumping time |  | - continuous pumping - large volume fracture stimulation treatments (e.g., shale gas) | - internal erosion causing barrier envelope failure - | 1 | 1 |  | - appropriate material selection to accommodate erosion to ensure AMP is not exceeded on the envelope (e.g. coatings)
11 |  |  |  | multiple fracture stimulation treatments in one wellbore |  | low permeability target zones that require multiple fractures for economic viability. | - failure of barrier envelope(s) due to pressure and temperature cycling | 1 | 1 |  | - consider the installation of a fracture string or a tie-back string in the wellbore - install barrier elements - improve cement,
12 |  |  |  | casing coupling separates |  | plastic formations, corrosion, erosion, over-torqued connections, under-torqued connections, manufactured defects, casing damage during installation, excessive doglegs overstresses casing, inadequate pressure testing, pressure cycling/fatigue, temperature fluctuations (pumping cold fluids, pumping hot fluids) | - loss of production capability - pressure migration or communication / interzonal flow | 1 | 1 |  | - review installation practices - suitability of selected coupling
13 |  |  |  | leak in the casing while fracturing with coiled tubing |  | leak uphole in the casing/liner caused an erosional hole in coiled tubing | leak in coil was not identified until there was a leak at surface, unidentified loss of coiled tubing integrity | 1 | 1 |  | Coiled tubing integrity check prior to removing coil
14 |  |  |  | higher treatment pressures than expected |  | fracture treatment screen-out, high breakdown/initiation pressures, high-pressure fracturing, inadequate equipment spec (shear pins) | AMP exceeded, higher fracture pressure than estimated | 1 | 1 |  | - ensure conservative estimate of maximum treating pressure
15 |  |  |  | fracture port fails to open |  | inadequate equipment spec (shear pins), inadequate equipment assembly, inadequate installation, fracture-ball failure due to pumping too high of rate | cycling of pressure causes fatigue failure of equipment, excessive treatment pressures | 1 | 1
16 |  |  |  | squeeze perforations or casing patch perforations |  | previous casing repair | leak | 1 | 1
17 |  |  |  | unable to close wellhead while under pressure (well control) |  | obstruction in the wellhead, proppant in the valve, poor valve maintenance | loss of well control, injury to people, damage to equipment, property, environment | 1 | 1 |  | systematic maintenance program suitable to continuous fracture operations and large fracture volumes. Ability to have redundant closing barriers that are remotely actuated.
18 |  |  |  | loss of wellhead integrity (body and connections) |  | washouts due to large proppant volumes, inappropriate wellhead for the operation, vibration or bending of large wellheads during pumping operation | loss of well control, injury to people, damage to equipment, property, environment | 1 | 1 |  | select appropriate wellhead and connections for operations, systematic iron inspection process, for large high pressure frac trees add anchoring to secure against vibration and bending loads
19 |  |  |  | Wellbore deformation or shearing |  | Following a seismic event | Loss of wellbore integrity | 1 | 1 |  | wellbore integrity must be re-assessed by pressure testing casing and potentially caliper logging to gauge any casing deformation that may have occurred. Subsequent milling may reduce yield strength and require modification of stimulation design for additional stages in the subject and offsetting wells.
20 |  |  |  | wellhead wear |  | high erosional velocities of particulate matter | loss of wellhead integrity | 1 | 1 |  | wellhead designed with opposing flows or sacrificial wear plate

## Interwellbore Communication (hidden)
Item | Sub IRP | Category | Position | Hazard Scenario What is existing? | Applicable | Cause How can this happen? | Threats / Consequences What events/incidents can result? | HSE | NPT | Required HSE Critical Controls / Safeguards | Industry Suggested Controls and Mitigations How can this be prevented? | Actions to be taken / By Who and When | Frequency of Exposure | Probability of Loss | Consequences | Risk Ranking | Operational Phase | Primary Responsible Party | Related to Item
1 | Other |  |  | Frac equipment refueling hose/line leaks | Y | - Hose/line failure due to fittings incorrectly installed - Hose/line not integrity tested prior to use - Fatigue failure of hose/line - Hose/line degradation due to lack of proper inspection process - Damage to fuel lines/hose from mobile equipment on wellsite | - Hose/line failure due to fittings incorrectly installed - Hose/line not integrity tested prior to use - Fatigue failure of hose/line - Hose/line degradation due to lack of proper inspection process - Damage to fuel lines/hose from mobile equipment on wellsite |  |  |  | -appropriate fire suppression on location (number of fire trucks for number of pumps)
2 | Other |  |  | Treating Line failure | Y | -Screenout, plugged line, frozen line, electronic failure, improper trip settings, relief valve failure, overpressure, washout, improper rig-in, miss-matched unions | - Fire and explosion - Harm to personnel - Lost time and cost - Damage to equipment |  |  | Pressure relief valve, | Pressure relief valve, iron mgmt and testing standards, rig-in standards (sufficient flexibility, tie-downs, flow capacity etc), flowback requirements, no personnel in high pressure zone
3 | Other |  |  | Chemical Spill | Y | -Valve failure, rupture of tote, line failure, washout, seal failure | Environmental, harm to personnel, lost time and cost |  |  | - PPE, fire suppression equipment, containment in chem vans, shower units | - Control toxicity of chemicals being used/chemical substitution, visual inspection of chem add hoses, stainless steel fittings (engineering controls), spill kits and training, order of addition for chemicals
4 | Other |  |  | Fire in chem van | Y | -release of low flash point chemical, use of alcohol to suppress freeze point, frozen chem add line, mixture of incompatible products | -Environment, harm to personnel, fire, damage to equipment |  |  | - PPE, fire suppression equipment, containment in chem vans, shower units | -Standards for chem add packages in specific environments, standards for segregation of products during transport
5 | Other |  |  | Well control failure at wellhead | Y | Wellhead component failure, treating line failure, testing equipment failure, overpressure, washout, communication with offsetting well | - Fire and explosion - Harm to personnel - Lost time and cost - Damage to equipment |  |  |  | - Remote operated wellhead valve, redundant wellhead valves, treesaver, properly configured wellhead stacks (large enough ports/connections)
6 | Other |  |  | CO2/N2 release | Y | -Suction hose failure, containment vessel failure, treating line failure | Harm to personnel, damage to equipment |  |  | Proper venting/relief valves on tanks, iron & hose testing/standards | -Standard for tank bleedoff at end of job
7 | Other |  |  | Packing failure | Y | Improper maintenance, improper packing, wrong packing material, inadequate lubrication | - Fire and explosion - Harm to personnel - Lost time and cost - Damage to equipment |  |  | Maintenance standards, training, Pump ESD's | -Head tarps, pump covers
8 | Simultaneous Operations |  |  | Concurrent operation | Y | Small leases, multiple wells per lease, efficiency |  |  |  |  | -Wellhead spacing regulations, consideration for acceptable simultaneous ops, egress plans
9 | Other |  |  | Pumping recirculated fluids | Y |  | H2S exposure, flammability, damage to equipment/treating iron, unknown contaminants (required PPE) |  |  |  | -standard for frac water, MSDS requirement, minimum sampling and testing requirements
10 | Other |  |  | Prolonged exposure to silica sand | Y | Larger fracs and multiple zones require in the multiple of 10 times the volume of sand | Exposure above the OEL to workers of Silica sand |  |  | Increased PPE respiratory protection | Exposure monitoring, and health assessment monitoring.
11 | Other |  |  | High pressure frac line failure clean side | Y | water cannon effect
12 | Other |  |  | High pressure frac line failure dirty side | Y | cannon effective containing possible corrosives or sand
13 | Other |  |  | High pressure frac union or fitting failure | Y | both clean and dirty side
14 | Other |  |  | Ice plugs or hydrates forming in frac line | Y
15 | Other |  |  | High pressure lines whipping around following a failure or separation | Y
16 | Other |  |  | Chemical or corrosive release high volume/low volume | Y
17 | Other |  |  | Vapour release high volume or low volume, high pressure and low pressure (propane frac) | Y
18 | Other |  |  | The special case of hydraulic fracture stimulating in shallow wells, particularly those at target depths less than 600 m or within 300 m of the base of groundwater protection is cause for concern and very careful evaluations are required. | Y
1 |  |  |  | FPZ is Underestimated |  | - See Appendix A of IRP 24 document - Geology - Inadequate Modeling - Fracture Treatment Larger than planned - Multiple stages pumped into one stage unintentionally (inadequate stage isolation, frac goes only into one perforated interval on a multi-perforated stage, longitudinal frac, hz pancake frac) - Fracture Treatment type change from plan - Intersection of offset hydraulically fractured wellbores - FPZ reservoir depletion | - Loss of barrier integrity in an IOW - Unintentional interwellbore communication - Fault(s) can considerably extend fracture half length, thus increasing the likelihood of interwellbore communication to wells within the FPZ and beyond the FPZ (i.e., a fault can create FPZ estimation uncertainty) '- Packer or cement failing to isolate frac into desired interval - Ball activated system failure (ball not dropped, ball fails, downhole seat fails). Wrong ball dropped on sleeve. Extra ball in system accidentally left over from another well's frac operation - Friction diversion not working for limited entry frac - Seat is worn on ball/seat job so ball does not shift sleeve - Coil fraccing downhole isolation packer/tool fails and bypasses to previously fracced stages below it | 1 | 1 |  | - If faulting is anticipated, establish IOW well control plans based on a higher likelihood of interwellbore communication - Compile area experience for more accurate FPZ determination - Consider adding a fault related safety factor to intentionally expand the FPZ - If faulting is anticipated, consider all possible SCW's as at-risk - Micro-seismic to asses frac propagation behaviour when perforating multiple intervals for a single frac stage | [8 empty] | 1
2 |  |  |  | Adjusted Maximum Pressure (AMP) Overestimation |  | - No recent pressure integrity tests conducted - Challenges with determining Adjusted Maximum Pressure on a barrier flow path based on operational history of component (how to effectively derate a component) - Casing and/or downhole equipment integrity issues due to corrosion, erosion, service, & age - Wellhead integrity problems due to corrosion, erosion, service, and age | - Loss of barrier integrity in an IOW - Inadequate allowance for response times during wellsite operations to prevent adjusted maximum pressure from being exceeded - Pressure integrity reliability of threaded components | 1 | 1 |  | - Conduct pressure integrity tests to verify Adjusted Maximum Pressure - Replace (if possible) barrier components of concern that have been integrity tested to the Adjust Maximum Pressure.
3 |  |  |  | Adjusted Maximum Pressure (AMP) exceeded |  | - Rate of pressure increase in IOW too quick for effective reaction time during an interwellbore communication event '- Inadequate well control plan for IOW | - Loss of barrier integrity in an IOW - Low relative value of Adjusted Maximum Pressure in relation to potential pressures from interwellbore communication (excessive well control plan and associate cost) | 1 | 1 |  | - Use pressure relieving system on IOW for the case where a relatively low Adjusted Maximum Pressure as compared to potential pressures from interwellbore communication - Stop fracture treatment on subject well and immediately relieve pressure on subject well
4 |  |  |  | Pressure integrity test conducted in the opposite direction of flow |  | - Inability to test a barrier in a direction of flow due to wellbore configuration / construction - Interwellbore communication flow path opposite direction to what was planned for | - Barriers may have lower pressure integrity in the direction of flow (e.g., cemented perforations, bridge plugs, downhole isolation devices, etc.) - Can not monitor pressure below a barrier in the direction of flow | 1 | 1 |  | - If high probability of interwellbore communication and concerns with a barrier's integrity in the direction of flow, consider adjusting the Subject Well's frac design to reduce the interwellbore communication probability. - Consider adding a secondary barrier on a flow path
5 |  |  |  | IOW barrier fails to groundwater |  | - An interwellbore communication event’s pressure exceeds a groundwater barrier’s integrity capacity - Annular hydraulic isolation is inadequate between interwellbore communication flow path and groundwater | - Age and/or operating history of well has reduced the integrity capacity of barrier(s) - Intermediate or production casing annulus cement top is below base of groundwater (not cemented to surface) and surface casing shoe is set shallower than base of groundwater - Cement squeezed shallow zone perforations lose their integrity or have lost their integrity - Interwellbore communication to a non-energy well (i.e. water well) - Creation of a surface casing vent flow - Contamination event is not detected and/or goes undetected - Radioactive substances used for tracing purposes on Subject Well migrate into aquifer | 1 | 1 |  | - Follow IRP 24 Hazard Management Process for Interwellbore Communication - Follow Directive XX (Hydraulic Fracturing); Non-saline Aquifer protection and Hydraulic fracturing near water wells sections. - Consider adding a secondary barrier to groundwater - Avoid radioactive tracers when groundwater has only a primary barrier with no secondary barrier back-up
6 |  |  |  | IOW is Abandoned (Cut & Capped) |  | - Assumed the abandoned IOW completed with regulatory standards at the time of the abandonment - Assumed service, age, & type of barriers in wellbore | - Not able to effectively monitor this type of IOW - Most likely only able to reduce risks at this type of IOW by adjusting the Subject Well's fracture stimulation plan - An interwellbore communication event is not detected and/or goes undetected - The abandon wellbore penetrates or terminates near the target zone - Can not integrity test or protect this type of IOW barriers - Abandonment barrier(s) inadequate to contain interwellbore communication pressures - Age & service of the abandoned wellbore can have a affect on barrier(s) integrity - Severity of consequences of an interwellbore communication event | 1 | 1 |  | - Extensively scrutinize IOW abandonment quality and zonal penetrations to assess risk and then adjust the Subject Well's fracture stimulation plan to reduce the likelihood of interwellbore to as low as reasonably practicable - Avoid having any abandoned wells within an FPZ
7 |  |  |  | Interwellbore communication to a subsurface object other than a wellbore (i.e., mineshaft, cave, non-energy wellbore, etc) |  | - Unknown subsurface feature within the FPZ - Object is in close proximity to Subject Well | - Damage or flooding of mine or cave - Injury to personnel involved with subsurface feature - Uncontrolled release to surface - Water well and/or aquifer compromised | 1 | 1 |  | - Identify and risk assess all known subsurface features within FPZ - Put a control plan in place to reduce and mitigate the risk of interwellbore communication to offset feature
8 |  |  |  | Inadequate hydraulic isolation in IOW |  | - Inadequate historical drilling practices (lack of standards used on old wells) - Problems while drilling (i.e. loss circulation) - Historic operational issues - Cement and casing degradation due to wellbore fluids - Cement and casing degradation due to high pressure injection history | - Interwellbore communication path and/or mechanism to an Other Zone above the Target Zone - Reduction in barrier integrity - Ground water contamination | 1 | 1 |  | - If high probability of interwellbore communication and concerns hydraulic isolation, consider adjusting the Subject Well's fracture initiating point and/or frac design to reduce the interwellbore communication probability. - Remedially repair IOW's hydraulic isolation integrity
9 |  |  |  | IOW active downhole drilling operation encounters unexpected high pore pressure gradient |  | - IOW has active downhole operations (see Section 24.2.3.4) - An IOW active drilling operation drills into a hydraulic fracture that has retained pressures from a Subject Well's fracture treatment (unexpectedly high pore pressure gradient) | - Well control incident on IOW active downhole drilling operation - Subject well fracture stimulation operational timing changed from original plan and/or notification, but now coincides with active downhole drilling operation | 1 | 1 |  | - As part of the notification process, continuously check operational timings for changes and assess IOW's with active downhole operations have become at-risk as a result of changes to operational timings. - Avoid active IOW drilling operations for a reasonable period of time following a Subject Well's fracture stimulation operation - Ensure the drilling plans are prepared for and consider the possibility of drilling into a hydraulic fracture that has retained fracture stimulation pressures
10 |  |  |  | IOW has sour zones and/or is producing sour fluids |  | - IOW has sour zones and/or is producing for a sour zone below the Subject Well target zone and an interwellbore communication comprises a well's integrity such that sour fluids can migrate | - Sour fluids communicating to Subject Well and/or an IOW that is not designed for handling sour fluids. | 1 | 1 |  | - Extensive risk assessment and barrier analysis for development of more comprehensive well control plans in the event of interwellbore communication
11 |  |  |  | Maximum pressure pulses at IOWs occur after the subject well frac pumping operations have shutdown (a delayed response) |  | - High pressure from subject well frac takes time to migrate through the reservoir to the IOW | - Monitoring and response action is planned for during the subject well frac operations, but this event can occur post frac when monitoring and response preparation is not in place. | 1 | 1 |  | - Area experience needs to be risk assessed for this type of reservoir response at an IOW
12
13
14

## Interwellbore
Item | Sub IRP | Category | Position | Hazard Scenario | Applicable | Cause | Threats / Consequences | HSE | NPT | Required HSE Critical Controls / Safeguards | Industry Suggested Controls and Mitigations | Actions to be taken / By Who and When | Frequency of Exposure | Probability of Loss | Consequences | Risk Ranking | Operational Phase | Primary Responsible Party | Related to Item
1 | Other |  |  | Frac equipment refueling hose/line leaks | Y | - Hose/line failure due to fittings incorrectly installed - Hose/line not integrity tested prior to use - Fatigue failure of hose/line - Hose/line degradation due to lack of proper inspection process - Damage to fuel lines/hose from mobile equipment on wellsite | - Hose/line failure due to fittings incorrectly installed - Hose/line not integrity tested prior to use - Fatigue failure of hose/line - Hose/line degradation due to lack of proper inspection process - Damage to fuel lines/hose from mobile equipment on wellsite |  |  |  | -appropriate fire suppression on location (number of fire trucks for number of pumps)
2 | Other |  |  | Treating Line failure | Y | -Screenout, plugged line, frozen line, electronic failure, improper trip settings, relief valve failure, overpressure, washout, improper rig-in, miss-matched unions | - Fire and explosion - Harm to personnel - Lost time and cost - Damage to equipment |  |  | Pressure relief valve, | Pressure relief valve, iron mgmt and testing standards, rig-in standards (sufficient flexibility, tie-downs, flow capacity etc), flowback requirements, no personnel in high pressure zone
3 | Other |  |  | Chemical Spill | Y | -Valve failure, rupture of tote, line failure, washout, seal failure | Environmental, harm to personnel, lost time and cost |  |  | - PPE, fire suppression equipment, containment in chem vans, shower units | - Control toxicity of chemicals being used/chemical substitution, visual inspection of chem add hoses, stainless steel fittings (engineering controls), spill kits and training, order of addition for chemicals
4 | Other |  |  | Fire in chem van | Y | -release of low flash point chemical, use of alcohol to suppress freeze point, frozen chem add line, mixture of incompatible products | -Environment, harm to personnel, fire, damage to equipment |  |  | - PPE, fire suppression equipment, containment in chem vans, shower units | -Standards for chem add packages in specific environments, standards for segregation of products during transport
5 | Other |  |  | Well control failure at wellhead | Y | Wellhead component failure, treating line failure, testing equipment failure, overpressure, washout, communication with offsetting well | - Fire and explosion - Harm to personnel - Lost time and cost - Damage to equipment |  |  |  | - Remote operated wellhead valve, redundant wellhead valves, treesaver, properly configured wellhead stacks (large enough ports/connections)
6 | Other |  |  | CO2/N2 release | Y | -Suction hose failure, containment vessel failure, treating line failure | Harm to personnel, damage to equipment |  |  | Proper venting/relief valves on tanks, iron & hose testing/standards | -Standard for tank bleedoff at end of job
7 | Other |  |  | Packing failure | Y | Improper maintenance, improper packing, wrong packing material, inadequate lubrication | - Fire and explosion - Harm to personnel - Lost time and cost - Damage to equipment |  |  | Maintenance standards, training, Pump ESD's | -Head tarps, pump covers
8 | Simultaneous Operations |  |  | Concurrent operation | Y | Small leases, multiple wells per lease, efficiency |  |  |  |  | -Wellhead spacing regulations, consideration for acceptable simultaneous ops, egress plans
9 | Other |  |  | Pumping recirculated fluids | Y |  | H2S exposure, flammability, damage to equipment/treating iron, unknown contaminants (required PPE) |  |  |  | -standard for frac water, MSDS requirement, minimum sampling and testing requirements
10 | Other |  |  | Prolonged exposure to silica sand | Y | Larger fracs and multiple zones require in the multiple of 10 times the volume of sand | Exposure above the OEL to workers of Silica sand |  |  | Increased PPE respiratory protection | Exposure monitoring, and health assessment monitoring.
11 | Other |  |  | High pressure frac line failure clean side | Y | water cannon effect
12 | Other |  |  | High pressure frac line failure dirty side | Y | cannon effective containing possible corrosives or sand
13 | Other |  |  | High pressure frac union or fitting failure | Y | both clean and dirty side
14 | Other |  |  | Ice plugs or hydrates forming in frac line | Y
15 | Other |  |  | High pressure lines whipping around following a failure or separation | Y
16 | Other |  |  | Chemical or corrosive release high volume/low volume | Y
17 | Other |  |  | Vapour release high volume or low volume, high pressure and low pressure (propane frac) | Y
18 | Other |  |  | The special case of hydraulic fracture stimulating in shallow wells, particularly those at target depths less than 600 m or within 300 m of the base of groundwater protection is cause for concern and very careful evaluations are required. | Y
1 |  |  |  | FPZ is Underestimated |  | - See Appendix A of IRP 24 document - Geology - Inadequate Modeling - Fracture Treatment Larger than planned - Multiple stages pumped into one stage unintentionally (inadequate stage isolation, frac goes only into one perforated interval on a multi-perforated stage, longitudinal frac, hz pancake frac) - Fracture Treatment type change from plan - Intersection of offset hydraulically fractured wellbores - FPZ reservoir depletion | - Loss of barrier integrity in an IOW - Unintentional interwellbore communication - Fault(s) can considerably extend fracture half length, thus increasing the likelihood of interwellbore communication to wells within the FPZ and beyond the FPZ (i.e., a fault can create FPZ estimation uncertainty) '- Packer or cement failing to isolate frac into desired interval - Ball activated system failure (ball not dropped, ball fails, downhole seat fails). Wrong ball dropped on sleeve. Extra ball in system accidentally left over from another well's frac operation - Friction diversion not working for limited entry frac - Seat is worn on ball/seat job so ball does not shift sleeve - Coil fraccing downhole isolation packer/tool fails and bypasses to previously fracced stages below it | 1 | 1 |  | - If faulting is anticipated, establish IOW well control plans based on a higher likelihood of interwellbore communication - Compile area experience for more accurate FPZ determination - Consider adding a fault related safety factor to intentionally expand the FPZ - If faulting is anticipated, consider all possible SCW's as at-risk - Micro-seismic to asses frac propagation behaviour when perforating multiple intervals for a single frac stage | [8 empty] | 1
2 |  |  |  | Adjusted Maximum Pressure (AMP) Overestimation |  | - No recent pressure integrity tests conducted - Challenges with determining Adjusted Maximum Pressure on a barrier flow path based on operational history of component (how to effectively derate a component) - Casing and/or downhole equipment integrity issues due to corrosion, erosion, service, & age - Wellhead integrity problems due to corrosion, erosion, service, and age | - Loss of barrier integrity in an IOW - Inadequate allowance for response times during wellsite operations to prevent adjusted maximum pressure from being exceeded - Pressure integrity reliability of threaded components | 1 | 1 |  | - Conduct pressure integrity tests to verify Adjusted Maximum Pressure - Replace (if possible) barrier components of concern that have been integrity tested to the Adjust Maximum Pressure.
3 |  |  |  | Adjusted Maximum Pressure (AMP) exceeded |  | - Rate of pressure increase in IOW too quick for effective reaction time during an interwellbore communication event '- Inadequate well control plan for IOW | - Loss of barrier integrity in an IOW - Low relative value of Adjusted Maximum Pressure in relation to potential pressures from interwellbore communication (excessive well control plan and associate cost) | 1 | 1 |  | - Use pressure relieving system on IOW for the case where a relatively low Adjusted Maximum Pressure as compared to potential pressures from interwellbore communication - Stop fracture treatment on subject well and immediately relieve pressure on subject well
4 |  |  |  | Pressure integrity test conducted in the opposite direction of flow |  | - Inability to test a barrier in a direction of flow due to wellbore configuration / construction - Interwellbore communication flow path opposite direction to what was planned for | - Barriers may have lower pressure integrity in the direction of flow (e.g., cemented perforations, bridge plugs, downhole isolation devices, etc.) - Can not monitor pressure below a barrier in the direction of flow | 1 | 1 |  | - If high probability of interwellbore communication and concerns with a barrier's integrity in the direction of flow, consider adjusting the Subject Well's frac design to reduce the interwellbore communication probability. - Consider adding a secondary barrier on a flow path
5 |  |  |  | IOW barrier fails to groundwater |  | - An interwellbore communication event’s pressure exceeds a groundwater barrier’s integrity capacity - Annular hydraulic isolation is inadequate between interwellbore communication flow path and groundwater | - Age and/or operating history of well has reduced the integrity capacity of barrier(s) - Intermediate or production casing annulus cement top is below base of groundwater (not cemented to surface) and surface casing shoe is set shallower than base of groundwater - Cement squeezed shallow zone perforations lose their integrity or have lost their integrity - Interwellbore communication to a non-energy well (i.e. water well) - Creation of a surface casing vent flow - Contamination event is not detected and/or goes undetected - Radioactive substances used for tracing purposes on Subject Well migrate into aquifer | 1 | 1 |  | - Follow IRP 24 Hazard Management Process for Interwellbore Communication - Follow Directive XX (Hydraulic Fracturing); Non-saline Aquifer protection and Hydraulic fracturing near water wells sections. - Consider adding a secondary barrier to groundwater - Avoid radioactive tracers when groundwater has only a primary barrier with no secondary barrier back-up
6 |  |  |  | IOW is Abandoned (Cut & Capped) |  | - Assumed the abandoned IOW completed with regulatory standards at the time of the abandonment - Assumed service, age, & type of barriers in wellbore | - Not able to effectively monitor this type of IOW - Most likely only able to reduce risks at this type of IOW by adjusting the Subject Well's fracture stimulation plan - An interwellbore communication event is not detected and/or goes undetected - The abandon wellbore penetrates or terminates near the target zone - Can not integrity test or protect this type of IOW barriers - Abandonment barrier(s) inadequate to contain interwellbore communication pressures - Age & service of the abandoned wellbore can have a affect on barrier(s) integrity - Severity of consequences of an interwellbore communication event | 1 | 1 |  | - Extensively scrutinize IOW abandonment quality and zonal penetrations to assess risk and then adjust the Subject Well's fracture stimulation plan to reduce the likelihood of interwellbore to as low as reasonably practicable - Avoid having any abandoned wells within an FPZ
7 |  |  |  | Interwellbore communication to a subsurface object other than a wellbore (i.e., mineshaft, cave, non-energy wellbore, etc) |  | - Unknown subsurface feature within the FPZ - Object is in close proximity to Subject Well | - Damage or flooding of mine or cave - Injury to personnel involved with subsurface feature - Uncontrolled release to surface - Water well and/or aquifer compromised | 1 | 1 |  | - Identify and risk assess all known subsurface features within FPZ - Put a control plan in place to reduce and mitigate the risk of interwellbore communication to offset feature
8 |  |  |  | Inadequate hydraulic isolation in IOW |  | - Inadequate historical drilling practices (lack of standards used on old wells) - Problems while drilling (i.e. loss circulation) - Historic operational issues - Cement and casing degradation due to wellbore fluids - Cement and casing degradation due to high pressure injection history -IOW drilled on same pad and cased but does not yet have wellhead. | - Interwellbore communication path and/or mechanism to an Other Zone above the Target Zone - Reduction in barrier integrity - Ground water contamination | 1 | 1 |  | - If high probability of interwellbore communication and concerns hydraulic isolation, consider adjusting the Subject Well's fracture initiating point and/or frac design to reduce the interwellbore communication probability. - Remedially repair IOW's hydraulic isolation integrity
9 |  |  |  | IOW active downhole drilling operation encounters unexpected high pore pressure gradient |  | - IOW has active downhole operations (see Section 24.2.3.4) - An IOW active drilling operation drills into a hydraulic fracture that has retained pressures from a Subject Well's fracture treatment (unexpectedly high pore pressure gradient) | - Well control incident on IOW active downhole drilling operation - Subject well fracture stimulation operational timing changed from original plan and/or notification, but now coincides with active downhole drilling operation | 1 | 1 |  | - As part of the notification process, continuously check operational timings for changes and assess IOW's with active downhole operations have become at-risk as a result of changes to operational timings. - Avoid active IOW drilling operations for a reasonable period of time following a Subject Well's fracture stimulation operation - Ensure the drilling plans are prepared for and consider the possibility of drilling into a hydraulic fracture that has retained fracture stimulation pressures
10 |  |  |  | IOW has sour zones and/or is producing sour fluids |  | Improper maintenance, improper packing, wrong packing material, inadequate lubrication | - Sour fluids communicating to Subject Well and/or an IOW that is not designed for handling sour fluids. | 1 | 1 |  | - Extensive risk assessment and barrier analysis for development of more comprehensive well control plans in the event of interwellbore communication
11 |  |  |  | Maximum pressure pulses at IOWs occur after the subject well frac pumping operations have shutdown (a delayed response) |  | - High pressure from subject well frac takes time to migrate through the reservoir to the IOW | - Monitoring and response action is planned for during the subject well frac operations, but this event can occur post frac when monitoring and response preparation is not in place. | 1 | 1 |  | - Area experience needs to be risk assessed for this type of reservoir response at an IOW

## Surface Operations
Item | Sub IRP | Category | Position | Hazard Scenario What is existing? | Applicable | Cause How can this happen? | Threats / Consequences What events/incidents can result? | HSE | NPT | Required HSE Critical Controls / Safeguards | Industry Suggested Controls and Mitigations How can this be prevented? | Actions to be taken / By Who and When | Frequency of Exposure | Probability of Loss | Consequences | Risk Ranking | Operational Phase | Primary Responsible Party | Related to Item
12 |  |  |  | vehicular collisions |  | poor roads (icy), inexperienced drivers, congested locations, excessive traffic, worker incompetency | injury to people, damage to equipment, property, environment | 1 | 1 |  | follow hours of service, use of land guides, driver training and mentorship programs, barriers, traffic controllers
13 |  |  |  | insufficient egress / evacuation routes |  | congested location | inability to expedite evacuation | 1 | 1 |  | plan the site to accommodate the completion and required egress and evacuation, adequately space equipment during fracture operations to ensure egress and evacuation routes are maintained, communicate evacuation routes and egress in safety meetings, provide signage appropriately, (refer to IRP 20: Wellsite Design Spacing Requirements) | [7 empty] | 24.1.4.1 Lease Spacing
14 |  |  |  | surface fresh water spill |  | equipment failure or operator error / competency | waste of water, environmental impact (e.g., road wash out, run off), create muddy or icy conditions | 1 | 1 |  | equipment maintenance, operator training
15 |  |  |  | non-fresh water spill (produced, flowback, brine) |  | equipment failure or operator error / competency | environmental impact, waste of fluid, creats muddy or icy conditions | 1 | 1 |  | equipment maintenance, operator training, edged drip trays around areas prone to leaks (e.g., valves, blender, high pressure iron connection during rig out)
16 |  |  |  | excessive road dust over lengthy duration |  | increased trucking traffic to support the fracture operation | public relations, road damage, poor visibility for drivers | 1 | 1 |  | reduce driving speed, spray roads for dust control, modify traffic patterns, alternative routes
17 |  |  |  | increased risk and noise due to excessive access route(s) trucking traffic, particularly nearby public areas (schools, etc.) |  | increased trucking traffic to support the fracture operation | public relations, road damage, excessive noise, poor visibility for drivers, increased risk of traffic collision | 1 | 1 |  | reduce driving speed, modify traffic/convoy patterns, alternative routes, restrict hours of travel
18 |  |  |  | loss of primary containment |  | erosion, over-pressuring, chemical degradation, mechanical stress, connection not made-up correctly, faulty seals, physical damage, operator error / competency | injury to people, damage to equipment, property, environment | 1 | 1 |  | systematic iron inspection process, training, visual inspections, safety mechanisims in addition to human reaction that ensure pressure never exceeds the lowermost AMP. These mechanisims should take into account the reaction time to account for rates, fluid compressibility and tubular volumes | [7 empty] | 24.4.4 Surface Operations Hazard Management Planning
19 |  |  |  | unable to close wellhead while under pressure (well control) |  | obstruction in the wellhead, proppant in the valve, poor valve maintenance | loss of well control, injury to people, damage to equipment, property, environment | 1 | 1 |  | systematic maintenance program suitable to continuous fracture operations and large fracture volumes. Ability to have redundant closing barriers.
20 |  |  |  | unable to close wellhead while under pressure (well control) |  | obstruction in the wellhead, proppant in the valve, poor valve maintenance | loss of well control, injury to people, damage to equipment, property, environment | 1 | 1 |  | Systematic maintenance program suitable to continuous fracture operations and large fracture volumes.Consider remotely actuated valves if there are access issues to the valves, or if the frac fluid is extremely flammable or energized
20 |  |  |  | loss of wellhead integrity (body and connections) |  | washouts due to large proppant volumes, inappropriate wellhead for the operation | loss of well control, injury to people, damage to equipment, property, environment | 1 | 1 |  | select appropriate wellhead and connections for operations, systematic iron inspection process,
21 |  |  |  | N2 / CO2 displacing O2 from work area |  | equipment failure or operator error | injury to people or fatality | 1 | 1 |  | personnel training and awareness, communication to personnel in the area and at safety meetings. Adhearance to OH&S 244(1)&(2) | [7 empty] | 24.4.4 Surface Operations Hazard Management Planning
22 |  |  |  | potential energy of N2 / CO2 during an uncontrolled release |  | equipment failure or operator error / competency | injury to people or fatality | 1 | 1 |  | systematic iron inspection process, operator training, visual inspections, ensure pressure is relieved and communicated to personnel consider iron restraint system capable of containing the energy released during the loss of primary containment at maximum pressure and rate. | [7 empty] | 24.4.4 Surface Operations Hazard Management Planning
23 |  |  |  | CO2 ice plugs, trapped pressure |  | operator error / competency | injury to people or fatality, damage to equipment, property, | 1 | 1 |  | personnel training and awareness, communication to personnel in the area and at safety meetings
24 |  |  |  | human exposure to toxic chemicals |  | equipment failure, operator error / competency | injury to people or fatality | 1 | 1 |  | adequate ventilation, appropriate storage (WHIMIS guidelines), equipment inspection and maintenance, personnel training (WHIMIS training) and awareness , communication to personnel in the area and at safety meetings. the boundaries of the hazardous location are clearly identified to warn workers of the nature of the hazards associated procedures put in place to prevent workers entering areas where they could be exposed to harmful substances without authorization. | [7 empty] | 24.4.2 Surface Operations Area Determination
25 |  |  |  | oxidizer or fracture chemical spill |  | equipment failure, operator error / competency and lack of training | injury to people or fatality, fire (oxidizers, etc.), damage to equipment, property, and environment | 1 | 1 |  | refer to WHIMIS guidelines, communication to personnel in the area and at safety meetings, edged drip trays around areas prone to leaks (e.g., valves, blender, chemical connections during rig out)
26 |  |  |  | silica exposure |  | silica dust in the air | carcinogenic effects, longterm exposure resulting in respiratory ailments | 1 | 1 |  | mechanical silica dust control system, PPE (dust mask, goggles, respirators), non-pneumatic transferring of proppant, control and minimize people working in the area
27 |  |  |  | radiation exposure |  | radiation source in the densiometer | radiation exposure | 1 | 1 |  | proper handling (WHIMIS)
28 |  |  |  | fire during hot fueling |  | running equipment igniting a fuel release | fire, fatality, injury to personnel, loss or damage to equipment, environment or property | 1 | 1 |  | operator training, hot fueling procedure (JSA), onsite communication protocol , proper equipment, wellsite firetrucks present and monitoring operations, appropriate egress, hot fuel systems outfitted with emergency shut down. In the event of total depressurization of the line the system shuts down (see 24.3.5 Fracture Stimulation Execution, refer to IRP 8: Pumping of Flammable Fluids) | [7 empty] | 24.4.5 Fracture Stimulation Execution
29 |  |  |  | fire during fracture operations due to uncontrolled relase of flammable fluids |  | operator error / competency, Equipment Failure | fire, fatality, injury to personnel, loss or damage to equipment, environment or property | 1 | 1 |  | fit for purpose equipment design and specialized systems that would include: remote monitoring of high pressure areas during pumping, remote LEL system calibrated to the specific fluid being pumped, integrated ESD system that can be activated remotely, compartementalization of system to reduce amount of fluid released in the event of a leak. see IRP 8: Pumping of Flammable Fluids
30 |  |  |  | load falling on people or equipment in congested areas |  | equipment failure or operator error / competency with suspended loads | fatality, injury to personnel, loss or damage to equipment, property | 1 | 1 |  | appropriate equipment for the job, certifcation of lift equipment, certification of operator, personnal training and awareness during suspended load operations, use of tag lines
31 |  |  |  | hearing damage due to excess noise exposure |  | occupational hazard due to multiple diesel engines running concurrently during opertions | hearing loss | 1 | 1 |  | PPE (hearing protection) according to OHS
32 |  |  |  | difficulty communicating messages due to excess noise |  | loud | miscommunication leading to injury to personnel, damage to equipment, environment or property | 1 | 1 |  | effective communications plan and equipment capable of dampening the ambiant noise so instructions over the wireless sytems are clear
33 |  |  |  | flowback spills |  | equipment failure or operator error / competency, errosion, overpressuring | environmental impact, waste of fluid | 1 | 1 |  | equipment maintenance and inspection, operator training, proper storage and handling
34 |  |  |  | flowback vapours and odours |  | fugitive emissions, equipment failure, operator error, inexperience, inappropriately demarkated areas, open tanks | injury to people or fatality, fire, exposure to H2S and environmental impact | 1 | 1 |  | adequate ventilation, use of LEL / H2S monitors, personnel training, communication to personnel in the area and at safety meetings
35 |  |  |  | concurrent operations |  | conjested Active Operations Area, personnel awareness of concurrent operations, | injury to people (lifting, slips, trips, falls), damage to equipment (vehicular collision), non-permitted personnel in HPA, non-permitted personnel completing a unassigned tasks | 1 | 1 |  | refer to IRP 24.3.5 Fracture Stimulation Execution, Ensure equipment placed on the ground for transfer is neat and egress routes are provided around the equipment, traffic plan/traffic control | [7 empty] | 24.4.4.2.3 Concurrent Operations 24.4.5 Fracture Stimulation Execution
36 |  |  |  | Inadvertent opening of wellhead valves |  | operator error / competency, poor communication | injury to people or fatality, damage to equipment | 1 | 1 |  | Clear communication around who has access to wellhead valves.
37 |  |  |  | Inadvertent opening of wellhead valves |  | Hydraulic actuated valves can creep open from the closed position | Loss of primary containment | 1 | 1 |  | Using balanced stem gate valves or manually lock closed mechanism to prevent hydraulic actuated valves from creeping open
38 |  |  |  | sand settling in valves or low spots in treating iron |  | fluid not continuously flowing or at a low enough rate that sand can settle out | If pressure transducer is filled with sand may result in a mis-reading, if a valve is filled with sand it cannot be closed or may not seal completely | 1 | 1 |  | the manifold should be designed such that there are two valves capable of isolating each wellhead from the manifold and that one of these valves should be actuated. In addition, the manifold should be designed in such a fashion as to reduce the number of “dead legs” or sections of pipe through which fluid will not flow through and therefore may plug with sand.

## Well Barrier Diagram - Oil Well (hidden)
Subject Well Barrier Schematic | [8 empty] | Date:
Well Name / UWI:
Location:
|  |  |  | Status: | Producing
[9 empty] | OEM | Adjusted
| Subject Well | [6 empty] | Barriers | Spec | Max Pressure
[9 empty] | (MPa) | (MPa)
[8 empty] | 1. Wellhead | 21 | 18
|  |  |  | 1 |  |  |  | 2. Tubing spool | 21 | 18
[8 empty] | 3. Surface casing | 4 | 4
[8 empty] | 4. Surface casing cement/annulus | untested | untested
|  |  | 2 |  |  |  |  | 5. Production casing | 32 | 21
[8 empty] | 6. Production casing cement / annulus | untested | untested
[8 empty] | 7. Liner* | n/a | n/a
[8 empty] | 8. Liner cement / annulus* | n/a | n/a
|  | 3 | [5 empty] | 9. Tubing* | 55 | 50
[8 empty] | 10. Packer* | 42 | 40
| 4 | [6 empty] | * if applicable
| 400m | [5 empty] | BGWP
| 500m | [5 empty] | Casing Shoe
|  | 750m |  |  |  | Cement Top
5
6
9
10
1800m
TARGET
ZONE
1900m

## Well Barrier Diagram - Inj Well (hidden)
Well Barrier Schematic | [12 empty] | Date:
Well Name / UWI:
Location:
[5 empty] | Status: | Wateflood Injection
* O = Open, C = Closed
[13 empty] | OEM | Adjusted | Barrier | IOW
| Existing Waterflood Injection Well | [10 empty] | Barriers | Capacity | Max Pressure | Status | Monitored
[13 empty] | (MPa) | (MPa) | *(O / C) | (Y / N)
Primary Dependent
Barrier System
[12 empty] | 1. Wellhead valve | 21 |  | C
[12 empty] | 2. Flowline tee | 21 |  | C
[12 empty] | 3. Tubing hanger seals | 21 |  | C
[5 empty] | 1 |  | 6 |  |  |  |  | 4. Prod casing head valves (a,b) | 21 |  | C
[5 empty] | 2 |  |  |  |  | 5 |  | 5. Flowline valve | 21 |  | C
[5 empty] | A | [6 empty] | 6. Flowline | 21 |  | C
3
Secondary Dependent
| 4a | [8 empty] | 4b |  | Barrier System
[8 empty] | C |  |  |  | A. Wellhead master valve | 21 |  | O
|  |  | F | [7 empty] | B | B. Surface casing vent valve | 3.5 |  | C
[5 empty] | G | [6 empty] | C. Prod casing hanger seals | 21 |  | C
[12 empty] | D. Prod casing cement / annulus | untested |  | C
[12 empty] | E. Surface Casing Shoe | 3.6 |  | C
(18 kPa/m frac gradient)
[9 empty] | E |  |  | F. Surface Casing | 3.6 |  | C
|  | 200m | [6 empty] | Casing Shoe |  |  | G. Prod casing (burst) | 28 |  | C
|  |  | 400m |  |  |  |  | BGWP
|  |  | 750m |  |  |  |  | Cement Top
D
1800m
EOR INJ
ZONE

## Introduction (2) (hidden)
IRP 24 Hazard Register
Column Headings
Column Letter
Item | A | Sequential item number for hazards in each operational phase.
Hazard Scenario What If | B | Single jeopardy statement used to identify potential problems due to failure in pre-job planning, training, procedures, or equipment failure.
Applicable | C | Choose "Y" if "Hazard Scenario What If" applies to operation and "N" if it does not.
Threats/Consequences | D | A list of the potential consequences (HSE and NPT) of the "what if" occurring.
HSE | E | The risk of a situation/event with the potential to cause harm (to people, assets, or the environment).
NPT | F | The risk of Non Productive Time (NPT), including lost time and costs, formation damage and/or any deviation from the plan.
Required HSE Critical Controls / Safeguards | G | Controls/safeguards, and detailed recommended practices for high risk HSE items and referenced to specific prescriptive IRP 24 enforced requirements.
Considerations | H | Recommendations, considerations, and informational statements on how to reduce, eliminate, or manage Medium/Low Risk HSE items and all NPT items.
Actions to be Taken / By Who and When | I | List of actions required to reduce/eliminate the potential occurrence and/or severity if the hazard cannot be eliminated entirely. Who = Party/parties responsible for each action assigned. When = Date by which the action is to be completed.
Operational Phase | J | Categorization of the hazard scenario by operational phase.
Primary Responsible Party | K | Categorization of the hazard scenario by primary responsible party.
Primary Category | L | Categorization of the hazard scenario by primary category (equipment, well program, etc.)
Risk Ranking - severity of the event (consequence multiplied by likelihood of occurrence)
1 |  | High Risk - Engineering, Procedures, and Training required to control/mitigate risk.
2 |  | Medium Risk - Procedures and Training required to control/mitigate risk. Should consider Engineering.
3 |  | Low Risk - Training required to control/mitigate risk. Should consider Engineering and Procedures.
General Notes about Register